## Dashboard
KPI PERFORMANCE DASHBOARD
Period : Feb 2024 – Oct 2025
KPI OVERVIEW
TOTAL PROJECTS |  |  |  | TOTAL TASKS |  |  | Completed Task | Completed Project |  |  | OVER-BUDGET TASKS |  |  | TASK COMPLETION %
100 |  |  |  | 300 |  |  | 87 | 26 |  |  | 7 |  |  | 29%
Across Portfolio |  |  |  | work items tracked |  |  | 29% Task Completed | 26% Project Completed |  |  | cost-control watchlist |  |  | tasks fully complete
EARNED VALUE |  |  |  | AVG PROGRESS |  |  | AVG DURATION | HOURS LOGGED |  |  | TASKS BILLED |  |  | PORTFOLIO CPI
1085090.24 |  |  |  | 63.61% |  |  | 148.47 | 5763 |  |  | 93 |  |  | 0.29
value of work performed |  |  |  | mean task completion |  |  | planned task length | Total Effort |  |  | of 300 have actuals |  |  | earned value / actual
TOTAL BUDGET |  |  |  | BUDGET UTILIZATION |  |  | ACTUAL SPEND | BUDGET AT RISK |  |  | ON-BUDGET RATE |  |  | COST VARIANCE
1687280 |  |  |  | 30.73% |  |  | 518421 | 16457 |  |  | 92.47% |  |  | 5084
allocated funds |  |  |  | spend vs budget |  |  | committed to date | overrun across 7 tasks |  |  | billed tasks within budget |  |  | favorable vs budget
PERFORMANCE OVERVIEW
Status x Priority - Task Heatmap |  |  |  |  | Project | Task | Project Name | Owner | Type | Budget | Actual | Overrun $ | % Over
| High | Medium | Low |  | P075 | T001 | Building a Park Project 075 | Ivy | Other | 8493 | 12398 | 3905 | 45.98%
Behind | 45 | 27 | 15 |  | P010 | T001 | Airport Expansion Project 010 | Grace | Other | 1577 | 4850 | 3273 | 207.5%
On Track | 44 | 19 | 12 |  | P096 | T002 | Office Building Renovation 096 | Frank | Renovation | 2984 | 6060 | 3076 | 103.1%
On Hold | 30 | 17 | 13 |  | P027 | T002 | University Dormitory Constr. 027 | Bob | Construction | 1646 | 4190 | 2544 | 154.6%
Completed | 37 | 28 | 13 |  | P094 | T003 | Road Expansion Project 094 | Charlie | Infrastructure | 1447 | 3357 | 1910 | 132%
Cell = task count; deeper red = higher concentration |  |  |  |  | P052 | T001 | Apartment Complex Dev. 052 | Ivy | Other | 8114 | 9104 | 990 | 12.2%
[5 empty] | P022 | T003 | Apartment Complex Dev. 022 | Ivy | Other | 1424 | 2183 | 759 | 53.3%
KEY INSIGHTS
▸ Spend is heavily back-loaded: only 30.7% of the $1.69M budget is committed to date, signalling an early-stage or schedule-delayed portfolio.
▸ Delivery risk is concentrated: 49 of 100 projects are Behind or On Hold, versus 26 Completed — nearly half the portfolio needs intervention.
▸ September 2024 is the spend peak at $148K (29% of all actual cost), worth investigating for cost spikes or milestone clustering.
▸ Workload is concentrated: Charlie and Alice carry 114 of 300 tasks (38%) and ~40% of logged hours — a key-person dependency risk.
▸ Cost control: 7 tasks are over budget by a combined $16.5K; High-priority items make up 52% of tasks, suggesting priority inflation.
▸ Overruns cluster in "Other" projects (4 of 7), led by Park P075 (+46%) and Airport P010 (+208%) - both warrant scope/estimate root-cause reviews before more cash is committed.
▸ Risk quadrant: "Other" ($555K) and "Renovation" ($395K) pair the largest budgets with the lowest average progress (~60-62%) - highest exposure, slowest burn.
▸ Resourcing is capacity-bound, not skill-bound: Frank leads on completion rate (44%) with the lightest load, while the two heaviest workloads (Charlie, Alice) sit near the portfolio-low ~26% - rebalancing should lift throughput.
▸ Schedule: average planned task duration is 148 days; Innovation runs longest (237 days), compounding its delivery risk and tying up budget for longer.
▸ Budget is geographically diversified - it takes ~10 of 13 states to reach 80% of spend - limiting single-location dependency but offering little vendor-consolidation leverage.

## Data Model
METRICS |  |  | Project Status | Projects | % Share |  | Project Type | Projects |  |  | Month | Actual Cost | Budget |  | Team Member | Tasks | Hours | Budget Owned |  | Location | Actual Cost | Budget | Tasks
Metric | Value |  | Completed | 26 | 26% |  | Renovation | 26 |  |  | Feb-24 | 27684 | 38961 |  | Frank | 16 | 337 | 77055 |  | Florida | 20954 | 103354 | 22
Total Projects | 100 |  | On Track | 25 | 25% |  | Innovation | 7 |  |  | Mar-24 | 28256 | 75357 |  | David | 26 | 436 | 129024 |  | Washington | 21153 | 86123 | 16
Total Tasks | 300 |  | Behind | 29 | 29% |  | Construction | 20 |  |  | Apr-24 | 46333 | 64913 |  | Bob | 25 | 473 | 145675 |  | North Carolina | 22793 | 110002 | 21
Total Budget | 1687280 |  | On Hold | 20 | 20% |  | Infrastructure | 7 |  |  | May-24 | 43446 | 73704 |  | Ivy | 39 | 608 | 228001 |  | California | 27162 | 132003 | 23
Actual Cost (Spent) | 518421 | [5 empty] | Maintenance | 7 |  |  | Jun-24 | 51099 | 98719 |  | Grace | 38 | 721 | 191912 |  | New Jersey | 32681 | 117417 | 22
Budget Utilization | 30.73% | [5 empty] | Other | 33 |  |  | Jul-24 | 84350 | 209148 |  | Eve | 42 | 884 | 240784 |  | New York | 33397 | 116224 | 21
Avg Task Progress | 63.61% |  | Task Status | Tasks | % Share | [5 empty] | Aug-24 | 69500 | 182429 |  | Alice | 54 | 1060 | 336554 |  | Georgia | 38636 | 143498 | 29
Total Hours Logged | 5763 |  | Completed | 87 | 29% | [5 empty] | Sep-24 | 148399 | 205771 |  | Charlie | 60 | 1244 | 338275 |  | Ohio | 38934 | 134056 | 23
Over-Budget Tasks | 7 |  | In Progress | 106 | 35.33% |  | Project Type | Budget | Actual Cost |  | Oct-24 | 0 | 60842 | [6 empty] | Texas | 40831 | 145497 | 22
Completed Tasks | 87 |  | Pending | 107 | 35.67% |  | Renovation | 395361 | 121771 |  | Nov-24 | 0 | 82297 | [6 empty] | Illinois | 42351 | 135609 | 20
Completed Projects | 26 | [5 empty] | Innovation | 115653 | 37593 |  | Dec-24 | 0 | 114337 | [6 empty] | Pennsylvania | 61894 | 127153 | 24
[7 empty] | Construction | 377893 | 124126 |  | Jan-25 | 6060 | 61154 | [6 empty] | Michigan | 65520 | 150533 | 24
|  |  | Priority | Tasks | % Share |  | Infrastructure | 125426 | 54186 |  | Feb-25 | 0 | 50053 | [6 empty] | Virginia | 72115 | 185811 | 33
|  |  | High | 156 | 52% |  | Maintenance | 117868 | 35203 |  | Mar-25 | 4190 | 92373
|  |  | Medium | 91 | 30.33% |  | Other | 555079 | 145542 |  | Apr-25 | 0 | 72955
|  |  | Low | 53 | 17.67% | [5 empty] | May-25 | 0 | 40492
[11 empty] | Jun-25 | 0 | 60409
[7 empty] | Project Type | Avg Progress |  |  | Jul-25 | 9104 | 25019
[7 empty] | Renovation | 59.9% |  |  | Aug-25 | 0 | 24450
[7 empty] | Innovation | 62.52% |  |  | Sep-25 | 0 | 37117
[7 empty] | Construction | 68.03% |  |  | Oct-25 | 0 | 16780
[7 empty] | Infrastructure | 69.24%
[7 empty] | Maintenance | 69.43%
[7 empty] | Other | 61.65%
METRICS |  |  | CUMULATIVE SPEND (S-CURVE) | [5 empty] | BUDGET PARETO — LOCATION |  |  |  | RISK SEGMENTS BY TYPE |  |  |  |  | PROGRESS DISTRIBUTION
Portfolio CPI (billed) | 0.99751 |  | Month | Actual | Cum Actual | Budget | Cum Budget |  | Location | Budget | Cumulative % |  | Type | Avg Progress | Budget | Hours |  | Completion Band | Tasks
Cost Variance (Favorable) | 5084 |  | Feb-24 | 27684 | 27684 | 38961 | 38961 |  | Virginia | 185811 | 12.41% |  | Renovation | 59.9% | 395361 | 1600 |  | 0-20% | 44
Budget at Risk (Overruns) | 16457 |  | Mar-24 | 28256 | 55940 | 75357 | 114318 |  | Michigan | 150533 | 22.46% |  | Innovation | 62.52% | 115653 | 450 |  | 20-40% | 41
Avg Task Duration (Days) | 148.47 |  | Apr-24 | 46333 | 102273 | 64913 | 179231 |  | Texas | 145497 | 32.17% |  | Construction | 68.03% | 377893 | 1089 |  | 40-60% | 45
Tasks Billed | 93 |  | May-24 | 43446 | 145719 | 73704 | 252935 |  | Georgia | 143498 | 41.75% |  | Infrastructure | 69.24% | 125426 | 436 |  | 60-80% | 46
On-Budget Rate | 92.47% |  | Jun-24 | 51099 | 196818 | 98719 | 351654 |  | Illinois | 135609 | 50.8% |  | Maintenance | 69.43% | 117868 | 454 |  | 80-99% | 36
Task Completion Rate | 29% |  | Jul-24 | 84350 | 281168 | 209148 | 560802 |  | Ohio | 134056 | 59.75% |  | Other | 61.65% | 555079 | 1734 |  | 100% | 88
Total Earned Value | 1085090.24 |  | Aug-24 | 69500 | 350668 | 182429 | 743231 |  | California | 132003 | 68.57%
|  |  | Sep-24 | 148399 | 499067 | 205771 | 949002 |  | Pennsylvania | 127153 | 77.06%
|  |  | Oct-24 | 0 | 499067 | 60842 | 1009844 |  | New Jersey | 117417 | 84.9%
|  |  | Nov-24 | 0 | 499067 | 82297 | 1092141 |  | New York | 116224 | 92.66%
|  |  | Dec-24 | 0 | 499067 | 114337 | 1206478 |  | North Carolina | 110002 | 100%
|  |  | Jan-25 | 6060 | 505127 | 61154 | 1267632 |  | Florida | 103354 | 106.9%
|  |  | Feb-25 | 0 | 505127 | 50053 | 1317685 |  | Washington | 86123 | 112.7%
|  |  | Mar-25 | 4190 | 509317 | 92373 | 1410058
|  |  | Apr-25 | 0 | 509317 | 72955 | 1483013
|  |  | May-25 | 0 | 509317 | 40492 | 1523505
|  |  | Jun-25 | 0 | 509317 | 60409 | 1583914
|  |  | Jul-25 | 9104 | 518421 | 25019 | 1608933
|  |  | Aug-25 | 0 | 518421 | 24450 | 1633383
|  |  | Sep-25 | 0 | 518421 | 37117 | 1670500
|  |  | Oct-25 | 0 | 518421 | 16780 | 1687280
TEAM EFFICIENCY
Member | Tasks | Completed | Completion % | Hrs/Task
Frank | 16 | 7 | 43.75% | 21.0625
Bob | 25 | 9 | 36% | 18.92
Eve | 42 | 13 | 30.95% | 21.0476
Ivy | 39 | 11 | 28.21% | 15.5897
Charlie | 60 | 16 | 26.67% | 20.7333
David | 26 | 7 | 26.92% | 16.7692
Alice | 54 | 14 | 25.93% | 19.6296
Grace | 38 | 10 | 26.32% | 18.9737

## Dataset
Project ID | Project Name | Project Type | Location | Start Date | End Date | Month | Month Name | Project Status | Priority | Task ID | Task Name | Task Status | Assigned To | Hours Spent | Budget | Actual Cost | Progress | Duration (Days) | Earned Value | Over Budget? | Overrun $ | Billed?
P001 | Renovation of a School Project 001 | Renovation | Texas | 2024-07-21 | 2024-08-08 | 2024-08-01 | Aug-24 | Behind | Medium | T001 | Task 001 of Renovation of a School Project 001 | In Progress | Bob | 12 | 9621 | 0 | 24% | 18 | 2309.04 | No | 0 | No
P001 | Renovation of a School Project 001 | Renovation | New Jersey | 2024-07-21 | 2024-08-12 | 2024-08-01 | Aug-24 | Behind | High | T002 | Task 002 of Renovation of a School Project 001 | In Progress | Charlie | 4 | 7814 | 0 | 56% | 22 | 4375.84 | No | 0 | No
P001 | Renovation of a School Project 001 | Renovation | Ohio | 2024-07-21 | 2024-08-10 | 2024-08-01 | Aug-24 | Behind | High | T003 | Task 003 of Renovation of a School Project 001 | Completed | Charlie | 5 | 1028 | 1011 | 100% | 20 | 1028 | No | 0 | Yes
P002 | Innovation of a Classroom Project 002 | Innovation | Pennsylvania | 2024-04-06 | 2025-07-12 | 2025-07-01 | Jul-25 | On Track | High | T001 | Task 001 of Innovation of a Classroom Project 002 | Pending | Charlie | 24 | 1530 | 0 | 33% | 462 | 504.9 | No | 0 | No
P002 | Innovation of a Classroom Project 002 | Innovation | New York | 2024-04-06 | 2025-06-26 | 2025-06-01 | Jun-25 | On Track | Medium | T002 | Task 002 of Innovation of a Classroom Project 002 | Pending | Charlie | 26 | 7201 | 0 | 32% | 446 | 2304.32 | No | 0 | No
P002 | Innovation of a Classroom Project 002 | Innovation | California | 2024-04-06 | 2025-03-25 | 2025-03-01 | Mar-25 | On Track | Low | T003 | Task 003 of Innovation of a Classroom Project 002 | In Progress | Alice | 28 | 9814 | 0 | 29% | 353 | 2846.06 | No | 0 | No
P003 | Construction of a Hospital Wing Project 003 | Construction | Pennsylvania | 2024-07-20 | 2024-08-22 | 2024-08-01 | Aug-24 | Completed | Low | T001 | Task 001 of Construction of a Hospital Wing Project 003 | Completed | Grace | 7 | 7981 | 7717 | 100% | 33 | 7981 | No | 0 | Yes
P003 | Construction of a Hospital Wing Project 003 | Construction | Virginia | 2024-07-20 | 2024-09-25 | 2024-09-01 | Sep-24 | Completed | Medium | T002 | Task 002 of Construction of a Hospital Wing Project 003 | Completed | Frank | 23 | 1032 | 637 | 100% | 67 | 1032 | No | 0 | Yes
P003 | Construction of a Hospital Wing Project 003 | Construction | Ohio | 2024-07-20 | 2024-08-22 | 2024-08-01 | Aug-24 | Completed | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 003 | Completed | Grace | 13 | 8546 | 8502 | 100% | 33 | 8546 | No | 0 | Yes
P004 | Road Expansion Project 004 | Infrastructure | Pennsylvania | 2024-04-25 | 2024-05-06 | 2024-05-01 | May-24 | Completed | Medium | T001 | Task 001 of Road Expansion Project 004 | Completed | Frank | 28 | 3728 | 3369 | 100% | 11 | 3728 | No | 0 | Yes
P004 | Road Expansion Project 004 | Infrastructure | Texas | 2024-04-25 | 2024-05-05 | 2024-05-01 | May-24 | Completed | High | T002 | Task 002 of Road Expansion Project 004 | In Progress | Charlie | 26 | 9707 | 0 | 99% | 10 | 9609.93 | No | 0 | No
P004 | Road Expansion Project 004 | Infrastructure | Texas | 2024-04-25 | 2024-05-10 | 2024-05-01 | May-24 | Completed | Medium | T003 | Task 003 of Road Expansion Project 004 | Pending | Charlie | 18 | 5712 | 0 | 74% | 15 | 4226.88 | No | 0 | No
P005 | Bridge Maintenance Project 005 | Maintenance | Michigan | 2024-06-30 | 2025-07-31 | 2025-07-01 | Jul-25 | Behind | Medium | T001 | Task 001 of Bridge Maintenance Project 005 | Pending | Charlie | 18 | 3453 | 0 | 78% | 396 | 2693.34 | No | 0 | No
P005 | Bridge Maintenance Project 005 | Maintenance | California | 2024-06-30 | 2024-08-02 | 2024-08-01 | Aug-24 | Behind | Medium | T002 | Task 002 of Bridge Maintenance Project 005 | Completed | Frank | 7 | 2896 | 2643 | 100% | 33 | 2896 | No | 0 | Yes
P005 | Bridge Maintenance Project 005 | Maintenance | Virginia | 2024-06-30 | 2025-06-30 | 2025-06-01 | Jun-25 | Behind | High | T003 | Task 003 of Bridge Maintenance Project 005 | Pending | Grace | 0 | 6463 | 0 | 4% | 365 | 258.52 | No | 0 | No
P006 | Office Building Renovation Project 006 | Renovation | Michigan | 2024-09-08 | 2024-09-11 | 2024-09-01 | Sep-24 | Behind | Low | T001 | Task 001 of Office Building Renovation Project 006 | Completed | Alice | 9 | 3206 | 2739 | 100% | 3 | 3206 | No | 0 | Yes
P006 | Office Building Renovation Project 006 | Renovation | North Carolina | 2024-09-08 | 2024-09-11 | 2024-09-01 | Sep-24 | Behind | Medium | T002 | Task 002 of Office Building Renovation Project 006 | Completed | Frank | 40 | 6477 | 6402 | 100% | 3 | 6477 | No | 0 | Yes
P006 | Office Building Renovation Project 006 | Renovation | Pennsylvania | 2024-09-08 | 2025-02-20 | 2025-02-01 | Feb-25 | Behind | High | T003 | Task 003 of Office Building Renovation Project 006 | In Progress | Charlie | 40 | 8634 | 0 | 7% | 165 | 604.38 | No | 0 | No
P007 | Apartment Complex Development Project 007 | Other | California | 2024-06-08 | 2024-11-17 | 2024-11-01 | Nov-24 | On Track | High | T001 | Task 001 of Apartment Complex Development Project 007 | Pending | Ivy | 32 | 2552 | 0 | 62% | 162 | 1582.24 | No | 0 | No
P007 | Apartment Complex Development Project 007 | Other | Florida | 2024-06-08 | 2024-11-29 | 2024-11-01 | Nov-24 | On Track | Medium | T002 | Task 002 of Apartment Complex Development Project 007 | Pending | Grace | 25 | 4699 | 0 | 85% | 174 | 3994.15 | No | 0 | No
P007 | Apartment Complex Development Project 007 | Other | Pennsylvania | 2024-06-08 | 2024-11-17 | 2024-11-01 | Nov-24 | On Track | Low | T003 | Task 003 of Apartment Complex Development Project 007 | Pending | Ivy | 10 | 1720 | 0 | 92% | 162 | 1582.4 | No | 0 | No
P008 | Commercial Center Construction Project 008 | Construction | Illinois | 2024-04-17 | 2024-09-13 | 2024-09-01 | Sep-24 | On Track | Medium | T001 | Task 001 of Commercial Center Construction Project 008 | Pending | Alice | 17 | 9458 | 0 | 59% | 149 | 5580.22 | No | 0 | No
P008 | Commercial Center Construction Project 008 | Construction | Washington | 2024-04-17 | 2024-11-05 | 2024-11-01 | Nov-24 | On Track | Low | T002 | Task 002 of Commercial Center Construction Project 008 | Pending | Charlie | 21 | 4735 | 0 | 26% | 202 | 1231.1 | No | 0 | No
P008 | Commercial Center Construction Project 008 | Construction | Georgia | 2024-04-17 | 2024-10-19 | 2024-10-01 | Oct-24 | On Track | High | T003 | Task 003 of Commercial Center Construction Project 008 | Pending | Charlie | 7 | 9460 | 0 | 45% | 185 | 4257 | No | 0 | No
P009 | Highway Reconstruction Project 009 | Other | Texas | 2024-04-27 | 2025-04-28 | 2025-04-01 | Apr-25 | On Hold | High | T001 | Task 001 of Highway Reconstruction Project 009 | Pending | Charlie | 35 | 6385 | 0 | 36% | 366 | 2298.6 | No | 0 | No
P009 | Highway Reconstruction Project 009 | Other | Virginia | 2024-04-27 | 2025-06-01 | 2025-06-01 | Jun-25 | On Hold | Medium | T002 | Task 002 of Highway Reconstruction Project 009 | Pending | Ivy | 2 | 7980 | 0 | 88% | 400 | 7022.4 | No | 0 | No
P009 | Highway Reconstruction Project 009 | Other | Ohio | 2024-04-27 | 2025-05-26 | 2025-05-01 | May-25 | On Hold | Low | T003 | Task 003 of Highway Reconstruction Project 009 | Pending | Charlie | 26 | 1106 | 0 | 97% | 394 | 1072.82 | No | 0 | No
P010 | Airport Expansion Project 010 | Other | New Jersey | 2024-02-14 | 2024-06-15 | 2024-06-01 | Jun-24 | On Track | High | T001 | Task 001 of Airport Expansion Project 010 | Pending | Grace | 32 | 1577 | 4850 | 10% | 122 | 157.7 | Yes | 3273 | Yes
P010 | Airport Expansion Project 010 | Other | Ohio | 2024-02-14 | 2024-06-08 | 2024-06-01 | Jun-24 | On Track | High | T002 | Task 002 of Airport Expansion Project 010 | Pending | Alice | 16 | 3110 | 0 | 70% | 115 | 2177 | No | 0 | No
P010 | Airport Expansion Project 010 | Other | Ohio | 2024-02-14 | 2024-05-26 | 2024-05-01 | May-24 | On Track | Low | T003 | Task 003 of Airport Expansion Project 010 | Pending | Charlie | 11 | 3432 | 0 | 60% | 102 | 2059.2 | No | 0 | No
P011 | Shopping Mall Renovation Project 011 | Renovation | Texas | 2024-08-05 | 2024-07-28 | 2024-07-01 | Jul-24 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 011 | In Progress | Eve | 15 | 3544 | 0 | 64% | -8 | 2268.16 | No | 0 | No
P011 | Shopping Mall Renovation Project 011 | Renovation | Georgia | 2024-08-05 | 2024-08-19 | 2024-08-01 | Aug-24 | Completed | High | T002 | Task 002 of Shopping Mall Renovation Project 011 | In Progress | Eve | 40 | 7808 | 0 | 44% | 14 | 3435.52 | No | 0 | No
P011 | Shopping Mall Renovation Project 011 | Renovation | Florida | 2024-08-05 | 2024-08-01 | 2024-08-01 | Aug-24 | Completed | High | T003 | Task 003 of Shopping Mall Renovation Project 011 | Pending | Alice | 1 | 1776 | 0 | 2% | -4 | 35.52 | No | 0 | No
P012 | University Dormitory Construction Project 012 | Construction | Georgia | 2024-01-27 | 2024-02-29 | 2024-02-01 | Feb-24 | Completed | High | T001 | Task 001 of University Dormitory Construction Project 012 | Completed | Frank | 15 | 1815 | 1679 | 100% | 33 | 1815 | No | 0 | Yes
P012 | University Dormitory Construction Project 012 | Construction | Ohio | 2024-01-27 | 2024-02-29 | 2024-02-01 | Feb-24 | Completed | High | T002 | Task 002 of University Dormitory Construction Project 012 | Completed | Bob | 40 | 8915 | 8464 | 100% | 33 | 8915 | No | 0 | Yes
P012 | University Dormitory Construction Project 012 | Construction | New York | 2024-01-27 | 2025-06-27 | 2025-06-01 | Jun-25 | Completed | Medium | T003 | Task 003 of University Dormitory Construction Project 012 | Pending | Alice | 18 | 9242 | 0 | 98% | 517 | 9057.16 | No | 0 | No
P013 | Sports Stadium Upgrade Project 013 | Other | Florida | 2024-09-02 | 2024-08-24 | 2024-08-01 | Aug-24 | On Hold | Medium | T001 | Task 001 of Sports Stadium Upgrade Project 013 | Completed | Alice | 12 | 9559 | 9379 | 100% | -9 | 9559 | No | 0 | Yes
P013 | Sports Stadium Upgrade Project 013 | Other | Michigan | 2024-09-02 | 2024-07-06 | 2024-07-01 | Jul-24 | On Hold | Medium | T002 | Task 002 of Sports Stadium Upgrade Project 013 | In Progress | Bob | 38 | 4795 | 0 | 28% | -58 | 1342.6 | No | 0 | No
P013 | Sports Stadium Upgrade Project 013 | Other | California | 2024-09-02 | 2024-07-28 | 2024-07-01 | Jul-24 | On Hold | Medium | T003 | Task 003 of Sports Stadium Upgrade Project 013 | In Progress | Alice | 6 | 5258 | 0 | 55% | -36 | 2891.9 | No | 0 | No
P014 | Public Library Renovation Project 014 | Renovation | Ohio | 2024-07-30 | 2024-12-20 | 2024-12-01 | Dec-24 | Behind | Low | T001 | Task 001 of Public Library Renovation Project 014 | In Progress | Grace | 31 | 8531 | 0 | 10% | 143 | 853.1 | No | 0 | No
P014 | Public Library Renovation Project 014 | Renovation | Ohio | 2024-07-30 | 2025-01-30 | 2025-01-01 | Jan-25 | Behind | Low | T002 | Task 002 of Public Library Renovation Project 014 | Pending | Charlie | 8 | 3564 | 0 | 82% | 184 | 2922.48 | No | 0 | No
P014 | Public Library Renovation Project 014 | Renovation | New Jersey | 2024-07-30 | 2024-12-29 | 2024-12-01 | Dec-24 | Behind | Medium | T003 | Task 003 of Public Library Renovation Project 014 | Pending | Charlie | 6 | 6213 | 0 | 22% | 152 | 1366.86 | No | 0 | No
P015 | Building a Park Project 015 | Other | Georgia | 2024-03-17 | 2024-04-19 | 2024-04-01 | Apr-24 | On Hold | High | T001 | Task 001 of Building a Park Project 015 | Completed | Ivy | 8 | 4714 | 4608 | 100% | 33 | 4714 | No | 0 | Yes
P015 | Building a Park Project 015 | Other | New Jersey | 2024-03-17 | 2024-04-19 | 2024-04-01 | Apr-24 | On Hold | Medium | T002 | Task 002 of Building a Park Project 015 | Completed | Charlie | 4 | 1026 | 528 | 100% | 33 | 1026 | No | 0 | Yes
P015 | Building a Park Project 015 | Other | North Carolina | 2024-03-17 | 2024-04-19 | 2024-04-01 | Apr-24 | On Hold | High | T003 | Task 003 of Building a Park Project 015 | Completed | Bob | 22 | 5365 | 5232 | 100% | 33 | 5365 | No | 0 | Yes
P016 | Renovation of a School Project 016 | Renovation | Georgia | 2024-02-18 | 2024-09-25 | 2024-09-01 | Sep-24 | Completed | Medium | T001 | Task 001 of Renovation of a School Project 016 | Completed | Bob | 5 | 3688 | 3610 | 100% | 220 | 3688 | No | 0 | Yes
P016 | Renovation of a School Project 016 | Renovation | Texas | 2024-02-18 | 2024-10-22 | 2024-10-01 | Oct-24 | Completed | High | T002 | Task 002 of Renovation of a School Project 016 | Pending | Eve | 27 | 3233 | 0 | 38% | 247 | 1228.54 | No | 0 | No
P016 | Renovation of a School Project 016 | Renovation | Florida | 2024-02-18 | 2024-09-15 | 2024-09-01 | Sep-24 | Completed | Medium | T003 | Task 003 of Renovation of a School Project 016 | Pending | Eve | 25 | 8366 | 0 | 55% | 210 | 4601.3 | No | 0 | No
P017 | Innovation of a Classroom Project 017 | Innovation | Virginia | 2024-02-04 | 2024-10-25 | 2024-10-01 | Oct-24 | On Track | Low | T001 | Task 001 of Innovation of a Classroom Project 017 | Pending | Eve | 40 | 1856 | 0 | 87% | 264 | 1614.72 | No | 0 | No
P017 | Innovation of a Classroom Project 017 | Innovation | Illinois | 2024-02-04 | 2024-09-23 | 2024-09-01 | Sep-24 | On Track | High | T002 | Task 002 of Innovation of a Classroom Project 017 | Completed | Charlie | 34 | 5620 | 5481 | 100% | 232 | 5620 | No | 0 | Yes
P017 | Innovation of a Classroom Project 017 | Innovation | Georgia | 2024-02-04 | 2024-10-14 | 2024-10-01 | Oct-24 | On Track | High | T003 | Task 003 of Innovation of a Classroom Project 017 | In Progress | Alice | 18 | 1904 | 0 | 62% | 253 | 1180.48 | No | 0 | No
P018 | Construction of a Hospital Wing Project 018 | Construction | Ohio | 2024-09-02 | 2024-03-05 | 2024-03-01 | Mar-24 | Behind | Medium | T001 | Task 001 of Construction of a Hospital Wing Project 018 | In Progress | Grace | 26 | 5908 | 0 | 66% | -181 | 3899.28 | No | 0 | No
P018 | Construction of a Hospital Wing Project 018 | Construction | North Carolina | 2024-09-02 | 2024-03-01 | 2024-03-01 | Mar-24 | Behind | Medium | T002 | Task 002 of Construction of a Hospital Wing Project 018 | In Progress | Grace | 37 | 2176 | 0 | 54% | -185 | 1175.04 | No | 0 | No
P018 | Construction of a Hospital Wing Project 018 | Construction | Pennsylvania | 2024-09-02 | 2024-02-25 | 2024-02-01 | Feb-24 | Behind | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 018 | Pending | Grace | 7 | 9002 | 0 | 20% | -190 | 1800.4 | No | 0 | No
P019 | Road Expansion Project 019 | Infrastructure | Texas | 2024-10-06 | 2024-12-30 | 2024-12-01 | Dec-24 | Behind | High | T001 | Task 001 of Road Expansion Project 019 | Pending | Grace | 11 | 6821 | 0 | 61% | 85 | 4160.81 | No | 0 | No
P019 | Road Expansion Project 019 | Infrastructure | Ohio | 2024-10-06 | 2024-09-25 | 2024-09-01 | Sep-24 | Behind | Medium | T002 | Task 002 of Road Expansion Project 019 | Completed | Ivy | 1 | 7324 | 7263 | 100% | -11 | 7324 | No | 0 | Yes
P019 | Road Expansion Project 019 | Infrastructure | Georgia | 2024-10-06 | 2024-12-24 | 2024-12-01 | Dec-24 | Behind | Medium | T003 | Task 003 of Road Expansion Project 019 | Pending | Charlie | 13 | 3099 | 0 | 46% | 79 | 1425.54 | No | 0 | No
P020 | Bridge Maintenance Project 020 | Maintenance | Michigan | 2024-10-04 | 2024-07-03 | 2024-07-01 | Jul-24 | Completed | Medium | T001 | Task 001 of Bridge Maintenance Project 020 | Completed | Eve | 18 | 7962 | 7526 | 100% | -93 | 7962 | No | 0 | Yes
P020 | Bridge Maintenance Project 020 | Maintenance | California | 2024-10-04 | 2024-08-02 | 2024-08-01 | Aug-24 | Completed | High | T002 | Task 002 of Bridge Maintenance Project 020 | In Progress | Grace | 36 | 7221 | 0 | 84% | -63 | 6065.64 | No | 0 | No
P020 | Bridge Maintenance Project 020 | Maintenance | Michigan | 2024-10-04 | 2024-07-02 | 2024-07-01 | Jul-24 | Completed | High | T003 | Task 003 of Bridge Maintenance Project 020 | Pending | Grace | 24 | 7256 | 0 | 11% | -94 | 798.16 | No | 0 | No
P021 | Office Building Renovation Project 021 | Renovation | North Carolina | 2024-03-21 | 2024-12-15 | 2024-12-01 | Dec-24 | Behind | High | T001 | Task 001 of Office Building Renovation Project 021 | In Progress | Alice | 26 | 8483 | 0 | 43% | 269 | 3647.69 | No | 0 | No
P021 | Office Building Renovation Project 021 | Renovation | Michigan | 2024-03-21 | 2024-09-25 | 2024-09-01 | Sep-24 | Behind | High | T002 | Task 002 of Office Building Renovation Project 021 | Completed | Frank | 21 | 2463 | 2091 | 100% | 188 | 2463 | No | 0 | Yes
P021 | Office Building Renovation Project 021 | Renovation | Georgia | 2024-03-21 | 2024-09-20 | 2024-09-01 | Sep-24 | Behind | High | T003 | Task 003 of Office Building Renovation Project 021 | Completed | Ivy | 15 | 8372 | 7940 | 100% | 183 | 8372 | No | 0 | Yes
P022 | Apartment Complex Development Project 022 | Other | Michigan | 2024-09-01 | 2024-04-11 | 2024-04-01 | Apr-24 | On Track | High | T001 | Task 001 of Apartment Complex Development Project 022 | In Progress | Ivy | 6 | 8903 | 0 | 68% | -143 | 6054.04 | No | 0 | No
P022 | Apartment Complex Development Project 022 | Other | California | 2024-09-01 | 2024-04-28 | 2024-04-01 | Apr-24 | On Track | Medium | T002 | Task 002 of Apartment Complex Development Project 022 | In Progress | Grace | 7 | 1255 | 0 | 28% | -126 | 351.4 | No | 0 | No
P022 | Apartment Complex Development Project 022 | Other | Virginia | 2024-09-01 | 2024-04-24 | 2024-04-01 | Apr-24 | On Track | High | T003 | Task 003 of Apartment Complex Development Project 022 | In Progress | Ivy | 18 | 1424 | 2183 | 77% | -130 | 1096.48 | Yes | 759 | Yes
P023 | Commercial Center Construction Project 023 | Construction | Virginia | 2024-04-01 | 2024-05-18 | 2024-05-01 | May-24 | Behind | High | T001 | Task 001 of Commercial Center Construction Project 023 | Pending | Alice | 17 | 3662 | 0 | 45% | 47 | 1647.9 | No | 0 | No
P023 | Commercial Center Construction Project 023 | Construction | North Carolina | 2024-04-01 | 2024-06-01 | 2024-06-01 | Jun-24 | Behind | Medium | T002 | Task 002 of Commercial Center Construction Project 023 | Pending | Charlie | 27 | 2437 | 0 | 2% | 61 | 48.74 | No | 0 | No
P023 | Commercial Center Construction Project 023 | Construction | Illinois | 2024-04-01 | 2024-04-10 | 2024-04-01 | Apr-24 | Behind | Low | T003 | Task 003 of Commercial Center Construction Project 023 | In Progress | Charlie | 19 | 7519 | 0 | 45% | 9 | 3383.55 | No | 0 | No
P024 | Highway Reconstruction Project 024 | Other | Illinois | 2024-08-16 | 2024-08-29 | 2024-08-01 | Aug-24 | Completed | Medium | T001 | Task 001 of Highway Reconstruction Project 024 | In Progress | Charlie | 1 | 5955 | 0 | 5% | 13 | 297.75 | No | 0 | No
P024 | Highway Reconstruction Project 024 | Other | Florida | 2024-08-16 | 2024-09-04 | 2024-09-01 | Sep-24 | Completed | Low | T002 | Task 002 of Highway Reconstruction Project 024 | Pending | Ivy | 1 | 1799 | 0 | 75% | 19 | 1349.25 | No | 0 | No
P024 | Highway Reconstruction Project 024 | Other | Michigan | 2024-08-16 | 2024-09-01 | 2024-09-01 | Sep-24 | Completed | Medium | T003 | Task 003 of Highway Reconstruction Project 024 | Completed | Eve | 24 | 8925 | 8659 | 100% | 16 | 8925 | No | 0 | Yes
P025 | Airport Expansion Project 025 | Other | Washington | 2024-05-05 | 2024-07-20 | 2024-07-01 | Jul-24 | On Hold | High | T001 | Task 001 of Airport Expansion Project 025 | Completed | Alice | 37 | 8938 | 8487 | 100% | 76 | 8938 | No | 0 | Yes
P025 | Airport Expansion Project 025 | Other | New Jersey | 2024-05-05 | 2024-07-17 | 2024-07-01 | Jul-24 | On Hold | Low | T002 | Task 002 of Airport Expansion Project 025 | In Progress | David | 10 | 8533 | 0 | 72% | 73 | 6143.76 | No | 0 | No
P025 | Airport Expansion Project 025 | Other | New York | 2024-05-05 | 2024-07-03 | 2024-07-01 | Jul-24 | On Hold | Medium | T003 | Task 003 of Airport Expansion Project 025 | In Progress | Charlie | 16 | 8402 | 0 | 50% | 59 | 4201 | No | 0 | No
P026 | Shopping Mall Renovation Project 026 | Renovation | Pennsylvania | 2024-08-07 | 2025-04-30 | 2025-04-01 | Apr-25 | On Hold | Low | T001 | Task 001 of Shopping Mall Renovation Project 026 | In Progress | Eve | 21 | 6524 | 0 | 10% | 266 | 652.4 | No | 0 | No
P026 | Shopping Mall Renovation Project 026 | Renovation | Illinois | 2024-08-07 | 2024-08-10 | 2024-08-01 | Aug-24 | On Hold | Medium | T002 | Task 002 of Shopping Mall Renovation Project 026 | Completed | Eve | 34 | 8061 | 8002 | 100% | 3 | 8061 | No | 0 | Yes
P026 | Shopping Mall Renovation Project 026 | Renovation | Georgia | 2024-08-07 | 2025-04-06 | 2025-04-01 | Apr-25 | On Hold | High | T003 | Task 003 of Shopping Mall Renovation Project 026 | Pending | Alice | 3 | 2436 | 0 | 82% | 242 | 1997.52 | No | 0 | No
P027 | University Dormitory Construction Project 027 | Construction | Michigan | 2024-03-01 | 2024-12-28 | 2024-12-01 | Dec-24 | Completed | High | T001 | Task 001 of University Dormitory Construction Project 027 | In Progress | Frank | 35 | 9670 | 0 | 84% | 302 | 8122.8 | No | 0 | No
P027 | University Dormitory Construction Project 027 | Construction | Washington | 2024-03-01 | 2025-03-22 | 2025-03-01 | Mar-25 | Completed | Low | T002 | Task 002 of University Dormitory Construction Project 027 | In Progress | Bob | 7 | 1646 | 4190 | 100% | 386 | 1646 | Yes | 2544 | Yes
P027 | University Dormitory Construction Project 027 | Construction | Ohio | 2024-03-01 | 2025-01-19 | 2025-01-01 | Jan-25 | Completed | Medium | T003 | Task 003 of University Dormitory Construction Project 027 | In Progress | Alice | 30 | 3853 | 0 | 19% | 324 | 732.07 | No | 0 | No
P028 | Sports Stadium Upgrade Project 028 | Other | California | 2024-07-25 | 2025-01-19 | 2025-01-01 | Jan-25 | Behind | Medium | T001 | Task 001 of Sports Stadium Upgrade Project 028 | Pending | Alice | 22 | 5266 | 0 | 31% | 178 | 1632.46 | No | 0 | No
P028 | Sports Stadium Upgrade Project 028 | Other | California | 2024-07-25 | 2025-05-28 | 2025-05-01 | May-25 | Behind | Medium | T002 | Task 002 of Sports Stadium Upgrade Project 028 | Pending | Bob | 16 | 4878 | 0 | 78% | 307 | 3804.84 | No | 0 | No
P028 | Sports Stadium Upgrade Project 028 | Other | New York | 2024-07-25 | 2025-01-16 | 2025-01-01 | Jan-25 | Behind | Low | T003 | Task 003 of Sports Stadium Upgrade Project 028 | Pending | David | 23 | 4589 | 0 | 98% | 175 | 4497.22 | No | 0 | No
P029 | Public Library Renovation Project 029 | Renovation | North Carolina | 2024-10-04 | 2024-05-13 | 2024-05-01 | May-24 | On Track | Low | T001 | Task 001 of Public Library Renovation Project 029 | Completed | Grace | 33 | 3498 | 3235 | 100% | -144 | 3498 | No | 0 | Yes
P029 | Public Library Renovation Project 029 | Renovation | Michigan | 2024-10-04 | 2024-12-21 | 2024-12-01 | Dec-24 | On Track | High | T002 | Task 002 of Public Library Renovation Project 029 | Pending | Charlie | 30 | 7342 | 0 | 15% | 78 | 1101.3 | No | 0 | No
P029 | Public Library Renovation Project 029 | Renovation | Virginia | 2024-10-04 | 2025-01-23 | 2025-01-01 | Jan-25 | On Track | High | T003 | Task 003 of Public Library Renovation Project 029 | Pending | Charlie | 22 | 3172 | 0 | 40% | 111 | 1268.8 | No | 0 | No
P030 | Building a Park Project 030 | Other | Washington | 2024-07-16 | 2024-07-29 | 2024-07-01 | Jul-24 | On Track | High | T001 | Task 001 of Building a Park Project 030 | Pending | Ivy | 33 | 8742 | 0 | 79% | 13 | 6906.18 | No | 0 | No
P030 | Building a Park Project 030 | Other | Pennsylvania | 2024-07-16 | 2024-07-29 | 2024-07-01 | Jul-24 | On Track | High | T002 | Task 002 of Building a Park Project 030 | Pending | Charlie | 1 | 4274 | 0 | 28% | 13 | 1196.72 | No | 0 | No
P030 | Building a Park Project 030 | Other | New York | 2024-07-16 | 2024-07-29 | 2024-07-01 | Jul-24 | On Track | High | T003 | Task 003 of Building a Park Project 030 | In Progress | Bob | 16 | 3338 | 0 | 7% | 13 | 233.66 | No | 0 | No
P031 | Renovation of a School Project 031 | Renovation | Illinois | 2024-03-19 | 2024-06-09 | 2024-06-01 | Jun-24 | On Track | High | T001 | Task 001 of Renovation of a School Project 031 | In Progress | Bob | 2 | 3147 | 0 | 45% | 82 | 1416.15 | No | 0 | No
P031 | Renovation of a School Project 031 | Renovation | Georgia | 2024-03-19 | 2024-06-06 | 2024-06-01 | Jun-24 | On Track | High | T002 | Task 002 of Renovation of a School Project 031 | In Progress | Eve | 11 | 8355 | 0 | 79% | 79 | 6600.45 | No | 0 | No
P031 | Renovation of a School Project 031 | Renovation | Georgia | 2024-03-19 | 2024-06-03 | 2024-06-01 | Jun-24 | On Track | Medium | T003 | Task 003 of Renovation of a School Project 031 | Completed | Eve | 5 | 4000 | 3595 | 100% | 76 | 4000 | No | 0 | Yes
P032 | Innovation of a Classroom Project 032 | Innovation | New Jersey | 2024-02-05 | 2025-02-26 | 2025-02-01 | Feb-25 | On Hold | High | T001 | Task 001 of Innovation of a Classroom Project 032 | In Progress | Eve | 12 | 4133 | 0 | 54% | 387 | 2231.82 | No | 0 | No
P032 | Innovation of a Classroom Project 032 | Innovation | New York | 2024-02-05 | 2025-04-16 | 2025-04-01 | Apr-25 | On Hold | Medium | T002 | Task 002 of Innovation of a Classroom Project 032 | Pending | Charlie | 4 | 8258 | 0 | 39% | 436 | 3220.62 | No | 0 | No
P032 | Innovation of a Classroom Project 032 | Innovation | Washington | 2024-02-05 | 2025-03-24 | 2025-03-01 | Mar-25 | On Hold | Low | T003 | Task 003 of Innovation of a Classroom Project 032 | In Progress | David | 33 | 3654 | 0 | 79% | 413 | 2886.66 | No | 0 | No
P033 | Construction of a Hospital Wing Project 033 | Construction | California | 2024-05-15 | 2024-09-25 | 2024-09-01 | Sep-24 | Behind | Low | T001 | Task 001 of Construction of a Hospital Wing Project 033 | Completed | David | 4 | 4561 | 4256 | 100% | 133 | 4561 | No | 0 | Yes
P033 | Construction of a Hospital Wing Project 033 | Construction | Texas | 2024-05-15 | 2024-10-18 | 2024-10-01 | Oct-24 | Behind | High | T002 | Task 002 of Construction of a Hospital Wing Project 033 | In Progress | Grace | 10 | 9743 | 0 | 71% | 156 | 6917.53 | No | 0 | No
P033 | Construction of a Hospital Wing Project 033 | Construction | New Jersey | 2024-05-15 | 2024-09-23 | 2024-09-01 | Sep-24 | Behind | High | T003 | Task 003 of Construction of a Hospital Wing Project 033 | Completed | David | 4 | 7316 | 7140 | 100% | 131 | 7316 | No | 0 | Yes
P034 | Road Expansion Project 034 | Infrastructure | Florida | 2024-06-13 | 2024-09-01 | 2024-09-01 | Sep-24 | Behind | High | T001 | Task 001 of Road Expansion Project 034 | Pending | Grace | 14 | 2342 | 0 | 47% | 80 | 1100.74 | No | 0 | No
P034 | Road Expansion Project 034 | Infrastructure | Ohio | 2024-06-13 | 2024-08-17 | 2024-08-01 | Aug-24 | Behind | High | T002 | Task 002 of Road Expansion Project 034 | Completed | Ivy | 22 | 5899 | 5436 | 100% | 65 | 5899 | No | 0 | Yes
P034 | Road Expansion Project 034 | Infrastructure | Pennsylvania | 2024-06-13 | 2024-08-21 | 2024-08-01 | Aug-24 | Behind | High | T003 | Task 003 of Road Expansion Project 034 | In Progress | Charlie | 32 | 8314 | 0 | 68% | 69 | 5653.52 | No | 0 | No
P035 | Bridge Maintenance Project 035 | Maintenance | New Jersey | 2024-06-28 | 2024-07-31 | 2024-07-01 | Jul-24 | On Hold | Medium | T001 | Task 001 of Bridge Maintenance Project 035 | Completed | Eve | 14 | 7361 | 7026 | 100% | 33 | 7361 | No | 0 | Yes
P035 | Bridge Maintenance Project 035 | Maintenance | Virginia | 2024-06-28 | 2024-07-31 | 2024-07-01 | Jul-24 | On Hold | Low | T002 | Task 002 of Bridge Maintenance Project 035 | Completed | Grace | 11 | 6901 | 6528 | 100% | 33 | 6901 | No | 0 | Yes
P035 | Bridge Maintenance Project 035 | Maintenance | New Jersey | 2024-06-28 | 2025-04-26 | 2025-04-01 | Apr-25 | On Hold | High | T003 | Task 003 of Bridge Maintenance Project 035 | Pending | David | 40 | 5183 | 0 | 29% | 302 | 1503.07 | No | 0 | No
P036 | Office Building Renovation Project 036 | Renovation | Michigan | 2024-03-26 | 2024-07-10 | 2024-07-01 | Jul-24 | Behind | High | T001 | Task 001 of Office Building Renovation Project 036 | In Progress | Alice | 8 | 1220 | 0 | 79% | 106 | 963.8 | No | 0 | No
P036 | Office Building Renovation Project 036 | Renovation | Georgia | 2024-03-26 | 2024-07-29 | 2024-07-01 | Jul-24 | Behind | Medium | T002 | Task 002 of Office Building Renovation Project 036 | Pending | Frank | 16 | 6005 | 0 | 64% | 125 | 3843.2 | No | 0 | No
P036 | Office Building Renovation Project 036 | Renovation | California | 2024-03-26 | 2024-06-28 | 2024-06-01 | Jun-24 | Behind | High | T003 | Task 003 of Office Building Renovation Project 036 | Completed | Ivy | 32 | 3891 | 3841 | 100% | 94 | 3891 | No | 0 | Yes
P037 | Apartment Complex Development Project 037 | Other | Virginia | 2024-01-16 | 2024-07-31 | 2024-07-01 | Jul-24 | Behind | Medium | T001 | Task 001 of Apartment Complex Development Project 037 | In Progress | Ivy | 12 | 9160 | 0 | 9% | 197 | 824.4 | No | 0 | No
P037 | Apartment Complex Development Project 037 | Other | Pennsylvania | 2024-01-16 | 2024-05-25 | 2024-05-01 | May-24 | Behind | High | T002 | Task 002 of Apartment Complex Development Project 037 | Completed | Grace | 15 | 1719 | 1494 | 100% | 130 | 1719 | No | 0 | Yes
P037 | Apartment Complex Development Project 037 | Other | Illinois | 2024-01-16 | 2024-06-13 | 2024-06-01 | Jun-24 | Behind | High | T003 | Task 003 of Apartment Complex Development Project 037 | Pending | Ivy | 2 | 5180 | 0 | 33% | 149 | 1709.4 | No | 0 | No
P038 | Commercial Center Construction Project 038 | Construction | Texas | 2024-01-15 | 2024-03-01 | 2024-03-01 | Mar-24 | Behind | Medium | T001 | Task 001 of Commercial Center Construction Project 038 | Pending | Alice | 14 | 8804 | 0 | 93% | 46 | 8187.72 | No | 0 | No
P038 | Commercial Center Construction Project 038 | Construction | Michigan | 2024-01-15 | 2024-03-19 | 2024-03-01 | Mar-24 | Behind | Low | T002 | Task 002 of Commercial Center Construction Project 038 | Completed | Charlie | 38 | 8552 | 8463 | 100% | 64 | 8552 | No | 0 | Yes
P038 | Commercial Center Construction Project 038 | Construction | Michigan | 2024-01-15 | 2024-03-04 | 2024-03-01 | Mar-24 | Behind | High | T003 | Task 003 of Commercial Center Construction Project 038 | In Progress | Charlie | 32 | 6348 | 0 | 21% | 49 | 1333.08 | No | 0 | No
P039 | Highway Reconstruction Project 039 | Other | Virginia | 2024-01-25 | 2024-03-23 | 2024-03-01 | Mar-24 | Completed | High | T001 | Task 001 of Highway Reconstruction Project 039 | Completed | Charlie | 39 | 5312 | 4818 | 100% | 58 | 5312 | No | 0 | Yes
P039 | Highway Reconstruction Project 039 | Other | Virginia | 2024-01-25 | 2024-03-31 | 2024-03-01 | Mar-24 | Completed | High | T002 | Task 002 of Highway Reconstruction Project 039 | Pending | Ivy | 2 | 9232 | 0 | 24% | 66 | 2215.68 | No | 0 | No
P039 | Highway Reconstruction Project 039 | Other | Michigan | 2024-01-25 | 2024-04-03 | 2024-04-01 | Apr-24 | Completed | Medium | T003 | Task 003 of Highway Reconstruction Project 039 | Completed | Eve | 6 | 3291 | 2824 | 100% | 69 | 3291 | No | 0 | Yes
P040 | Airport Expansion Project 040 | Other | Florida | 2024-01-26 | 2024-09-25 | 2024-09-01 | Sep-24 | Behind | Medium | T001 | Task 001 of Airport Expansion Project 040 | Pending | David | 21 | 4414 | 0 | 24% | 243 | 1059.36 | No | 0 | No
P040 | Airport Expansion Project 040 | Other | Virginia | 2024-01-26 | 2024-07-29 | 2024-07-01 | Jul-24 | Behind | Medium | T002 | Task 002 of Airport Expansion Project 040 | In Progress | David | 21 | 9998 | 0 | 29% | 185 | 2899.42 | No | 0 | No
P040 | Airport Expansion Project 040 | Other | Michigan | 2024-01-26 | 2024-08-14 | 2024-08-01 | Aug-24 | Behind | High | T003 | Task 003 of Airport Expansion Project 040 | Pending | Charlie | 21 | 4869 | 0 | 54% | 201 | 2629.26 | No | 0 | No
P041 | Shopping Mall Renovation Project 041 | Renovation | Pennsylvania | 2024-03-17 | 2024-03-21 | 2024-03-01 | Mar-24 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 041 | Completed | Eve | 32 | 3746 | 3514 | 100% | 4 | 3746 | No | 0 | Yes
P041 | Shopping Mall Renovation Project 041 | Renovation | Florida | 2024-03-17 | 2024-03-21 | 2024-03-01 | Mar-24 | Completed | Medium | T002 | Task 002 of Shopping Mall Renovation Project 041 | Pending | Eve | 30 | 5413 | 0 | 93% | 4 | 5034.09 | No | 0 | No
P041 | Shopping Mall Renovation Project 041 | Renovation | Georgia | 2024-03-17 | 2024-03-21 | 2024-03-01 | Mar-24 | Completed | Medium | T003 | Task 003 of Shopping Mall Renovation Project 041 | In Progress | Alice | 28 | 6416 | 0 | 80% | 4 | 5132.8 | No | 0 | No
P042 | University Dormitory Construction Project 042 | Construction | North Carolina | 2024-01-31 | 2024-05-29 | 2024-05-01 | May-24 | Behind | High | T001 | Task 001 of University Dormitory Construction Project 042 | In Progress | Frank | 32 | 5512 | 0 | 5% | 119 | 275.6 | No | 0 | No
P042 | University Dormitory Construction Project 042 | Construction | California | 2024-01-31 | 2024-07-30 | 2024-07-01 | Jul-24 | Behind | High | T002 | Task 002 of University Dormitory Construction Project 042 | Pending | Bob | 7 | 6632 | 0 | 36% | 181 | 2387.52 | No | 0 | No
P042 | University Dormitory Construction Project 042 | Construction | New Jersey | 2024-01-31 | 2024-08-02 | 2024-08-01 | Aug-24 | Behind | Medium | T003 | Task 003 of University Dormitory Construction Project 042 | Pending | Alice | 29 | 3321 | 0 | 66% | 184 | 2191.86 | No | 0 | No
P043 | Sports Stadium Upgrade Project 043 | Other | California | 2024-05-01 | 2024-06-02 | 2024-06-01 | Jun-24 | On Track | High | T001 | Task 001 of Sports Stadium Upgrade Project 043 | In Progress | Alice | 35 | 9960 | 0 | 28% | 32 | 2788.8 | No | 0 | No
P043 | Sports Stadium Upgrade Project 043 | Other | Virginia | 2024-05-01 | 2024-05-12 | 2024-05-01 | May-24 | On Track | High | T002 | Task 002 of Sports Stadium Upgrade Project 043 | Completed | Bob | 6 | 7019 | 6569 | 100% | 11 | 7019 | No | 0 | Yes
P043 | Sports Stadium Upgrade Project 043 | Other | North Carolina | 2024-05-01 | 2024-06-23 | 2024-06-01 | Jun-24 | On Track | High | T003 | Task 003 of Sports Stadium Upgrade Project 043 | Completed | David | 19 | 2549 | 2168 | 100% | 53 | 2549 | No | 0 | Yes
P044 | Public Library Renovation Project 044 | Renovation | Georgia | 2024-05-04 | 2024-07-30 | 2024-07-01 | Jul-24 | Behind | High | T001 | Task 001 of Public Library Renovation Project 044 | Pending | Grace | 34 | 4587 | 0 | 54% | 87 | 2476.98 | No | 0 | No
P044 | Public Library Renovation Project 044 | Renovation | New Jersey | 2024-05-04 | 2024-09-18 | 2024-09-01 | Sep-24 | Behind | Low | T002 | Task 002 of Public Library Renovation Project 044 | Completed | Charlie | 8 | 4629 | 4482 | 100% | 137 | 4629 | No | 0 | Yes
P044 | Public Library Renovation Project 044 | Renovation | Washington | 2024-05-04 | 2024-09-14 | 2024-09-01 | Sep-24 | Behind | High | T003 | Task 003 of Public Library Renovation Project 044 | In Progress | Charlie | 30 | 4113 | 0 | 6% | 133 | 246.78 | No | 0 | No
P045 | Building a Park Project 045 | Other | Ohio | 2024-11-06 | 2024-07-14 | 2024-07-01 | Jul-24 | Completed | Medium | T001 | Task 001 of Building a Park Project 045 | Completed | Ivy | 25 | 3423 | 3361 | 100% | -115 | 3423 | No | 0 | Yes
P045 | Building a Park Project 045 | Other | Texas | 2024-11-06 | 2025-02-25 | 2025-02-01 | Feb-25 | Completed | High | T002 | Task 002 of Building a Park Project 045 | In Progress | Charlie | 39 | 2297 | 0 | 55% | 111 | 1263.35 | No | 0 | No
P045 | Building a Park Project 045 | Other | Virginia | 2024-11-06 | 2024-07-14 | 2024-07-01 | Jul-24 | Completed | Low | T003 | Task 003 of Building a Park Project 045 | Completed | Bob | 39 | 2868 | 2425 | 100% | -115 | 2868 | No | 0 | Yes
P046 | Renovation of a School Project 046 | Renovation | California | 2024-06-13 | 2024-06-16 | 2024-06-01 | Jun-24 | Completed | High | T001 | Task 001 of Renovation of a School Project 046 | In Progress | Bob | 39 | 1771 | 0 | 51% | 3 | 903.21 | No | 0 | No
P046 | Renovation of a School Project 046 | Renovation | North Carolina | 2024-06-13 | 2024-06-16 | 2024-06-01 | Jun-24 | Completed | Medium | T002 | Task 002 of Renovation of a School Project 046 | Pending | Eve | 25 | 1781 | 0 | 43% | 3 | 765.83 | No | 0 | No
P046 | Renovation of a School Project 046 | Renovation | Florida | 2024-06-13 | 2024-06-18 | 2024-06-01 | Jun-24 | Completed | High | T003 | Task 003 of Renovation of a School Project 046 | In Progress | Eve | 11 | 7012 | 0 | 18% | 5 | 1262.16 | No | 0 | No
P047 | Innovation of a Classroom Project 047 | Innovation | Florida | 2024-06-27 | 2024-07-30 | 2024-07-01 | Jul-24 | On Hold | High | T001 | Task 001 of Innovation of a Classroom Project 047 | Completed | Eve | 36 | 2554 | 2262 | 100% | 33 | 2554 | No | 0 | Yes
P047 | Innovation of a Classroom Project 047 | Innovation | Illinois | 2024-06-27 | 2025-01-09 | 2025-01-01 | Jan-25 | On Hold | High | T002 | Task 002 of Innovation of a Classroom Project 047 | In Progress | Charlie | 24 | 8357 | 0 | 68% | 196 | 5682.76 | No | 0 | No
P047 | Innovation of a Classroom Project 047 | Innovation | Pennsylvania | 2024-06-27 | 2024-09-25 | 2024-09-01 | Sep-24 | On Hold | High | T003 | Task 003 of Innovation of a Classroom Project 047 | Completed | David | 18 | 9034 | 8655 | 100% | 90 | 9034 | No | 0 | Yes
P048 | Construction of a Hospital Wing Project 048 | Construction | Florida | 2024-09-06 | 2024-12-15 | 2024-12-01 | Dec-24 | Completed | High | T001 | Task 001 of Construction of a Hospital Wing Project 048 | In Progress | David | 35 | 5180 | 0 | 49% | 100 | 2538.2 | No | 0 | No
P048 | Construction of a Hospital Wing Project 048 | Construction | Virginia | 2024-09-06 | 2024-10-31 | 2024-10-01 | Oct-24 | Completed | Low | T002 | Task 002 of Construction of a Hospital Wing Project 048 | Pending | Grace | 14 | 5368 | 0 | 96% | 55 | 5153.28 | No | 0 | No
P048 | Construction of a Hospital Wing Project 048 | Construction | Florida | 2024-09-06 | 2024-11-02 | 2024-11-01 | Nov-24 | Completed | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 048 | In Progress | David | 4 | 3812 | 0 | 97% | 57 | 3697.64 | No | 0 | No
P049 | Road Expansion Project 049 | Infrastructure | Pennsylvania | 2024-02-07 | 2024-08-11 | 2024-08-01 | Aug-24 | Completed | Medium | T001 | Task 001 of Road Expansion Project 049 | Completed | Grace | 20 | 2237 | 2196 | 100% | 186 | 2237 | No | 0 | Yes
P049 | Road Expansion Project 049 | Infrastructure | Texas | 2024-02-07 | 2024-08-13 | 2024-08-01 | Aug-24 | Completed | Low | T002 | Task 002 of Road Expansion Project 049 | Pending | Ivy | 35 | 8742 | 0 | 44% | 188 | 3846.48 | No | 0 | No
P049 | Road Expansion Project 049 | Infrastructure | New York | 2024-02-07 | 2024-08-23 | 2024-08-01 | Aug-24 | Completed | Medium | T003 | Task 003 of Road Expansion Project 049 | Pending | Charlie | 8 | 2613 | 0 | 76% | 198 | 1985.88 | No | 0 | No
P050 | Bridge Maintenance Project 050 | Maintenance | Illinois | 2024-12-06 | 2024-07-22 | 2024-07-01 | Jul-24 | On Track | High | T001 | Task 001 of Bridge Maintenance Project 050 | In Progress | Eve | 38 | 9467 | 0 | 71% | -137 | 6721.57 | No | 0 | No
P050 | Bridge Maintenance Project 050 | Maintenance | Virginia | 2024-12-06 | 2024-07-25 | 2024-07-01 | Jul-24 | On Track | High | T002 | Task 002 of Bridge Maintenance Project 050 | Completed | Grace | 40 | 1380 | 1005 | 100% | -134 | 1380 | No | 0 | Yes
P050 | Bridge Maintenance Project 050 | Maintenance | Pennsylvania | 2024-12-06 | 2024-07-31 | 2024-07-01 | Jul-24 | On Track | High | T003 | Task 003 of Bridge Maintenance Project 050 | In Progress | David | 18 | 1169 | 0 | 9% | -128 | 105.21 | No | 0 | No
P051 | Office Building Renovation Project 051 | Renovation | Ohio | 2024-03-23 | 2024-12-12 | 2024-12-01 | Dec-24 | Behind | Low | T001 | Task 001 of Office Building Renovation Project 051 | Pending | Alice | 19 | 7063 | 0 | 3% | 264 | 211.89 | No | 0 | No
P051 | Office Building Renovation Project 051 | Renovation | Virginia | 2024-03-23 | 2024-09-25 | 2024-09-01 | Sep-24 | Behind | High | T002 | Task 002 of Office Building Renovation Project 051 | Completed | Frank | 27 | 3221 | 3074 | 100% | 186 | 3221 | No | 0 | Yes
P051 | Office Building Renovation Project 051 | Renovation | Florida | 2024-03-23 | 2024-10-21 | 2024-10-01 | Oct-24 | Behind | High | T003 | Task 003 of Office Building Renovation Project 051 | In Progress | Ivy | 12 | 1201 | 0 | 41% | 212 | 492.41 | No | 0 | No
P052 | Apartment Complex Development Project 052 | Other | Virginia | 2024-05-27 | 2025-07-27 | 2025-07-01 | Jul-25 | On Hold | Low | T001 | Task 001 of Apartment Complex Development Project 052 | In Progress | Ivy | 19 | 8114 | 9104 | 88% | 426 | 7140.32 | Yes | 990 | Yes
P052 | Apartment Complex Development Project 052 | Other | Ohio | 2024-05-27 | 2025-06-11 | 2025-06-01 | Jun-25 | On Hold | Low | T002 | Task 002 of Apartment Complex Development Project 052 | Pending | Grace | 14 | 7222 | 0 | 19% | 380 | 1372.18 | No | 0 | No
P052 | Apartment Complex Development Project 052 | Other | Illinois | 2024-05-27 | 2025-08-22 | 2025-08-01 | Aug-25 | On Hold | High | T003 | Task 003 of Apartment Complex Development Project 052 | In Progress | Ivy | 9 | 2022 | 0 | 63% | 452 | 1273.86 | No | 0 | No
P053 | Commercial Center Construction Project 053 | Construction | Texas | 2024-06-18 | 2024-11-27 | 2024-11-01 | Nov-24 | On Track | Low | T001 | Task 001 of Commercial Center Construction Project 053 | In Progress | Alice | 3 | 9700 | 0 | 48% | 162 | 4656 | No | 0 | No
P053 | Commercial Center Construction Project 053 | Construction | New Jersey | 2024-06-18 | 2024-10-21 | 2024-10-01 | Oct-24 | On Track | High | T002 | Task 002 of Commercial Center Construction Project 053 | Pending | Charlie | 21 | 7624 | 0 | 45% | 125 | 3430.8 | No | 0 | No
P053 | Commercial Center Construction Project 053 | Construction | Ohio | 2024-06-18 | 2024-11-07 | 2024-11-01 | Nov-24 | On Track | High | T003 | Task 003 of Commercial Center Construction Project 053 | Pending | Charlie | 6 | 9072 | 0 | 66% | 142 | 5987.52 | No | 0 | No
P054 | Highway Reconstruction Project 054 | Other | New Jersey | 2024-04-15 | 2024-12-26 | 2024-12-01 | Dec-24 | Behind | High | T001 | Task 001 of Highway Reconstruction Project 054 | Pending | Charlie | 25 | 6793 | 0 | 95% | 255 | 6453.35 | No | 0 | No
P054 | Highway Reconstruction Project 054 | Other | California | 2024-04-15 | 2025-03-06 | 2025-03-01 | Mar-25 | Behind | High | T002 | Task 002 of Highway Reconstruction Project 054 | Pending | Ivy | 33 | 2398 | 0 | 32% | 325 | 767.36 | No | 0 | No
P054 | Highway Reconstruction Project 054 | Other | New York | 2024-04-15 | 2025-04-29 | 2025-04-01 | Apr-25 | Behind | Low | T003 | Task 003 of Highway Reconstruction Project 054 | In Progress | Eve | 16 | 9449 | 0 | 75% | 379 | 7086.75 | No | 0 | No
P055 | Airport Expansion Project 055 | Other | Virginia | 2024-08-28 | 2025-04-21 | 2025-04-01 | Apr-25 | On Hold | High | T001 | Task 001 of Airport Expansion Project 055 | In Progress | David | 17 | 8386 | 0 | 36% | 236 | 3018.96 | No | 0 | No
P055 | Airport Expansion Project 055 | Other | Illinois | 2024-08-28 | 2025-08-28 | 2025-08-01 | Aug-25 | On Hold | High | T002 | Task 002 of Airport Expansion Project 055 | Pending | David | 29 | 4294 | 0 | 17% | 365 | 729.98 | No | 0 | No
P055 | Airport Expansion Project 055 | Other | Michigan | 2024-08-28 | 2025-09-05 | 2025-09-01 | Sep-25 | On Hold | High | T003 | Task 003 of Airport Expansion Project 055 | In Progress | Alice | 27 | 8340 | 0 | 9% | 373 | 750.6 | No | 0 | No
P056 | Shopping Mall Renovation Project 056 | Renovation | Pennsylvania | 2024-08-15 | 2024-09-25 | 2024-09-01 | Sep-24 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 056 | Completed | Eve | 25 | 3548 | 3528 | 100% | 41 | 3548 | No | 0 | Yes
P056 | Shopping Mall Renovation Project 056 | Renovation | California | 2024-08-15 | 2024-11-02 | 2024-11-01 | Nov-24 | Completed | Low | T002 | Task 002 of Shopping Mall Renovation Project 056 | In Progress | Eve | 23 | 9545 | 0 | 8% | 79 | 763.6 | No | 0 | No
P056 | Shopping Mall Renovation Project 056 | Renovation | Florida | 2024-08-15 | 2024-11-04 | 2024-11-01 | Nov-24 | Completed | High | T003 | Task 003 of Shopping Mall Renovation Project 056 | In Progress | Alice | 40 | 1449 | 0 | 19% | 81 | 275.31 | No | 0 | No
P057 | University Dormitory Construction Project 057 | Construction | North Carolina | 2024-03-23 | 2025-06-15 | 2025-06-01 | Jun-25 | On Track | Medium | T001 | Task 001 of University Dormitory Construction Project 057 | In Progress | Frank | 20 | 9728 | 0 | 15% | 449 | 1459.2 | No | 0 | No
P057 | University Dormitory Construction Project 057 | Construction | New York | 2024-03-23 | 2024-04-25 | 2024-04-01 | Apr-24 | On Track | High | T002 | Task 002 of University Dormitory Construction Project 057 | Completed | Bob | 6 | 6762 | 6621 | 100% | 33 | 6762 | No | 0 | Yes
P057 | University Dormitory Construction Project 057 | Construction | California | 2024-03-23 | 2024-12-29 | 2024-12-01 | Dec-24 | On Track | Low | T003 | Task 003 of University Dormitory Construction Project 057 | In Progress | Alice | 28 | 4093 | 0 | 66% | 281 | 2701.38 | No | 0 | No
P058 | Sports Stadium Upgrade Project 058 | Other | New Jersey | 2024-07-24 | 2024-08-26 | 2024-08-01 | Aug-24 | On Hold | High | T001 | Task 001 of Sports Stadium Upgrade Project 058 | Completed | Alice | 20 | 9027 | 8655 | 100% | 33 | 9027 | No | 0 | Yes
P058 | Sports Stadium Upgrade Project 058 | Other | Georgia | 2024-07-24 | 2025-09-04 | 2025-09-01 | Sep-25 | On Hold | Low | T002 | Task 002 of Sports Stadium Upgrade Project 058 | Pending | Bob | 10 | 4949 | 0 | 99% | 407 | 4899.51 | No | 0 | No
P058 | Sports Stadium Upgrade Project 058 | Other | Georgia | 2024-07-24 | 2025-07-06 | 2025-07-01 | Jul-25 | On Hold | Low | T003 | Task 003 of Sports Stadium Upgrade Project 058 | Pending | David | 3 | 1671 | 0 | 93% | 347 | 1554.03 | No | 0 | No
P059 | Public Library Renovation Project 059 | Renovation | North Carolina | 2024-08-02 | 2024-08-31 | 2024-08-01 | Aug-24 | On Hold | High | T001 | Task 001 of Public Library Renovation Project 059 | Pending | Grace | 2 | 1634 | 0 | 47% | 29 | 767.98 | No | 0 | No
P059 | Public Library Renovation Project 059 | Renovation | Pennsylvania | 2024-08-02 | 2024-07-24 | 2024-07-01 | Jul-24 | On Hold | High | T002 | Task 002 of Public Library Renovation Project 059 | Completed | Alice | 34 | 9178 | 8962 | 100% | -9 | 9178 | No | 0 | Yes
P059 | Public Library Renovation Project 059 | Renovation | Ohio | 2024-08-02 | 2024-07-13 | 2024-07-01 | Jul-24 | On Hold | High | T003 | Task 003 of Public Library Renovation Project 059 | Completed | Charlie | 33 | 5369 | 4897 | 100% | -20 | 5369 | No | 0 | Yes
P060 | Building a Park Project 060 | Other | Georgia | 2024-04-07 | 2024-11-16 | 2024-11-01 | Nov-24 | On Hold | Medium | T001 | Task 001 of Building a Park Project 060 | Pending | Ivy | 8 | 4383 | 0 | 44% | 223 | 1928.52 | No | 0 | No
P060 | Building a Park Project 060 | Other | Texas | 2024-04-07 | 2024-09-25 | 2024-09-01 | Sep-24 | On Hold | High | T002 | Task 002 of Building a Park Project 060 | Completed | Alice | 5 | 9106 | 8788 | 100% | 171 | 9106 | No | 0 | Yes
P060 | Building a Park Project 060 | Other | Washington | 2024-04-07 | 2024-10-26 | 2024-10-01 | Oct-24 | On Hold | High | T003 | Task 003 of Building a Park Project 060 | In Progress | Bob | 34 | 7376 | 0 | 37% | 202 | 2729.12 | No | 0 | No
P061 | Renovation of a School Project 061 | Renovation | Georgia | 2024-06-14 | 2025-05-05 | 2025-05-01 | May-25 | On Hold | Low | T001 | Task 001 of Renovation of a School Project 061 | Pending | Bob | 31 | 4564 | 0 | 84% | 325 | 3833.76 | No | 0 | No
P061 | Renovation of a School Project 061 | Renovation | New Jersey | 2024-06-14 | 2025-05-21 | 2025-05-01 | May-25 | On Hold | Medium | T002 | Task 002 of Renovation of a School Project 061 | In Progress | Eve | 34 | 6685 | 0 | 25% | 341 | 1671.25 | No | 0 | No
P061 | Renovation of a School Project 061 | Renovation | New Jersey | 2024-06-14 | 2025-09-07 | 2025-09-01 | Sep-25 | On Hold | Medium | T003 | Task 003 of Renovation of a School Project 061 | In Progress | Eve | 36 | 3548 | 0 | 0% | 450 | 0 | No | 0 | No
P062 | Innovation of a Classroom Project 062 | Innovation | Washington | 2024-07-27 | 2025-03-24 | 2025-03-01 | Mar-25 | On Hold | High | T001 | Task 001 of Innovation of a Classroom Project 062 | Pending | Eve | 11 | 5997 | 0 | 11% | 240 | 659.67 | No | 0 | No
P062 | Innovation of a Classroom Project 062 | Innovation | New York | 2024-07-27 | 2024-09-25 | 2024-09-01 | Sep-24 | On Hold | High | T002 | Task 002 of Innovation of a Classroom Project 062 | Completed | Charlie | 16 | 3180 | 3081 | 100% | 60 | 3180 | No | 0 | Yes
P062 | Innovation of a Classroom Project 062 | Innovation | New York | 2024-07-27 | 2025-02-22 | 2025-02-01 | Feb-25 | On Hold | High | T003 | Task 003 of Innovation of a Classroom Project 062 | Pending | David | 38 | 2178 | 0 | 15% | 210 | 326.7 | No | 0 | No
P063 | Construction of a Hospital Wing Project 063 | Construction | Pennsylvania | 2024-07-16 | 2025-01-07 | 2025-01-01 | Jan-25 | On Track | High | T001 | Task 001 of Construction of a Hospital Wing Project 063 | In Progress | David | 5 | 2944 | 0 | 55% | 175 | 1619.2 | No | 0 | No
P063 | Construction of a Hospital Wing Project 063 | Construction | California | 2024-07-16 | 2024-08-18 | 2024-08-01 | Aug-24 | On Track | High | T002 | Task 002 of Construction of a Hospital Wing Project 063 | Completed | Grace | 31 | 7376 | 6945 | 100% | 33 | 7376 | No | 0 | Yes
P063 | Construction of a Hospital Wing Project 063 | Construction | Florida | 2024-07-16 | 2025-04-11 | 2025-04-01 | Apr-25 | On Track | Low | T003 | Task 003 of Construction of a Hospital Wing Project 063 | In Progress | David | 2 | 6433 | 0 | 68% | 269 | 4374.44 | No | 0 | No
P064 | Road Expansion Project 064 | Infrastructure | Texas | 2024-06-22 | 2024-09-25 | 2024-09-01 | Sep-24 | Behind | Low | T001 | Task 001 of Road Expansion Project 064 | Completed | Grace | 30 | 5551 | 5315 | 100% | 95 | 5551 | No | 0 | Yes
P064 | Road Expansion Project 064 | Infrastructure | Illinois | 2024-06-22 | 2024-07-25 | 2024-07-01 | Jul-24 | Behind | Medium | T002 | Task 002 of Road Expansion Project 064 | Completed | Ivy | 6 | 9127 | 8751 | 100% | 33 | 9127 | No | 0 | Yes
P064 | Road Expansion Project 064 | Infrastructure | Virginia | 2024-06-22 | 2024-09-25 | 2024-09-01 | Sep-24 | Behind | High | T003 | Task 003 of Road Expansion Project 064 | Completed | Charlie | 40 | 9168 | 9025 | 100% | 95 | 9168 | No | 0 | Yes
P065 | Bridge Maintenance Project 065 | Maintenance | New York | 2024-06-01 | 2024-02-08 | 2024-02-01 | Feb-24 | On Track | High | T001 | Task 001 of Bridge Maintenance Project 065 | Completed | Eve | 18 | 2284 | 2142 | 100% | -114 | 2284 | No | 0 | Yes
P065 | Bridge Maintenance Project 065 | Maintenance | Florida | 2024-06-01 | 2024-10-25 | 2024-10-01 | Oct-24 | On Track | Medium | T002 | Task 002 of Bridge Maintenance Project 065 | In Progress | Grace | 26 | 4973 | 0 | 41% | 146 | 2038.93 | No | 0 | No
P065 | Bridge Maintenance Project 065 | Maintenance | North Carolina | 2024-06-01 | 2024-09-30 | 2024-09-01 | Sep-24 | On Track | High | T003 | Task 003 of Bridge Maintenance Project 065 | Pending | Alice | 26 | 7992 | 0 | 60% | 121 | 4795.2 | No | 0 | No
P066 | Office Building Renovation Project 066 | Renovation | Georgia | 2024-04-05 | 2024-11-23 | 2024-11-01 | Nov-24 | Completed | High | T001 | Task 001 of Office Building Renovation Project 066 | In Progress | Alice | 32 | 3669 | 0 | 53% | 232 | 1944.57 | No | 0 | No
P066 | Office Building Renovation Project 066 | Renovation | Georgia | 2024-04-05 | 2024-11-06 | 2024-11-01 | Nov-24 | Completed | High | T002 | Task 002 of Office Building Renovation Project 066 | Pending | Frank | 20 | 6395 | 0 | 55% | 215 | 3517.25 | No | 0 | No
P066 | Office Building Renovation Project 066 | Renovation | North Carolina | 2024-04-05 | 2024-09-13 | 2024-09-01 | Sep-24 | Completed | Medium | T003 | Task 003 of Office Building Renovation Project 066 | Pending | Ivy | 1 | 4445 | 0 | 61% | 161 | 2711.45 | No | 0 | No
P067 | Apartment Complex Development Project 067 | Other | Washington | 2024-01-30 | 2025-01-12 | 2025-01-01 | Jan-25 | Completed | Low | T001 | Task 001 of Apartment Complex Development Project 067 | In Progress | Ivy | 10 | 1599 | 0 | 4% | 348 | 63.96 | No | 0 | No
P067 | Apartment Complex Development Project 067 | Other | Texas | 2024-01-30 | 2024-12-26 | 2024-12-01 | Dec-24 | Completed | Medium | T002 | Task 002 of Apartment Complex Development Project 067 | In Progress | Grace | 4 | 9597 | 0 | 71% | 331 | 6813.87 | No | 0 | No
P067 | Apartment Complex Development Project 067 | Other | New York | 2024-01-30 | 2024-03-03 | 2024-03-01 | Mar-24 | Completed | High | T003 | Task 003 of Apartment Complex Development Project 067 | Completed | Ivy | 8 | 2143 | 1984 | 100% | 33 | 2143 | No | 0 | Yes
P068 | Commercial Center Construction Project 068 | Construction | New York | 2024-01-30 | 2025-05-28 | 2025-05-01 | May-25 | Behind | Low | T001 | Task 001 of Commercial Center Construction Project 068 | Pending | Alice | 28 | 6658 | 0 | 48% | 484 | 3195.84 | No | 0 | No
P068 | Commercial Center Construction Project 068 | Construction | Illinois | 2024-01-30 | 2025-02-13 | 2025-02-01 | Feb-25 | Behind | Low | T002 | Task 002 of Commercial Center Construction Project 068 | Pending | Charlie | 32 | 8758 | 0 | 93% | 380 | 8144.94 | No | 0 | No
P068 | Commercial Center Construction Project 068 | Construction | California | 2024-01-30 | 2024-03-03 | 2024-03-01 | Mar-24 | Behind | High | T003 | Task 003 of Commercial Center Construction Project 068 | Completed | Charlie | 8 | 9806 | 9477 | 100% | 33 | 9806 | No | 0 | Yes
P069 | Highway Reconstruction Project 069 | Other | Washington | 2024-02-25 | 2025-03-01 | 2025-03-01 | Mar-25 | On Track | High | T001 | Task 001 of Highway Reconstruction Project 069 | Pending | Charlie | 16 | 3424 | 0 | 28% | 370 | 958.72 | No | 0 | No
P069 | Highway Reconstruction Project 069 | Other | North Carolina | 2024-02-25 | 2025-08-14 | 2025-08-01 | Aug-25 | On Track | High | T002 | Task 002 of Highway Reconstruction Project 069 | In Progress | Ivy | 36 | 8166 | 0 | 13% | 536 | 1061.58 | No | 0 | No
P069 | Highway Reconstruction Project 069 | Other | North Carolina | 2024-02-25 | 2025-08-08 | 2025-08-01 | Aug-25 | On Track | Low | T003 | Task 003 of Highway Reconstruction Project 069 | Pending | Eve | 3 | 9968 | 0 | 50% | 530 | 4984 | No | 0 | No
P070 | Airport Expansion Project 070 | Other | California | 2024-02-28 | 2025-06-23 | 2025-06-01 | Jun-25 | Behind | High | T001 | Task 001 of Airport Expansion Project 070 | In Progress | Alice | 0 | 9313 | 0 | 98% | 481 | 9126.74 | No | 0 | No
P070 | Airport Expansion Project 070 | Other | Michigan | 2024-02-28 | 2025-09-27 | 2025-09-01 | Sep-25 | Behind | High | T002 | Task 002 of Airport Expansion Project 070 | In Progress | David | 21 | 4494 | 0 | 11% | 577 | 494.34 | No | 0 | No
P070 | Airport Expansion Project 070 | Other | Florida | 2024-02-28 | 2024-04-01 | 2024-04-01 | Apr-24 | Behind | High | T003 | Task 003 of Airport Expansion Project 070 | Completed | Alice | 26 | 7738 | 7435 | 100% | 33 | 7738 | No | 0 | Yes
P071 | Shopping Mall Renovation Project 071 | Renovation | Virginia | 2024-10-02 | 2024-02-18 | 2024-02-01 | Feb-24 | On Track | High | T001 | Task 001 of Shopping Mall Renovation Project 071 | Completed | Eve | 32 | 8568 | 8546 | 100% | -227 | 8568 | No | 0 | Yes
P071 | Shopping Mall Renovation Project 071 | Renovation | Texas | 2024-10-02 | 2024-02-19 | 2024-02-01 | Feb-24 | On Track | High | T002 | Task 002 of Shopping Mall Renovation Project 071 | In Progress | Eve | 3 | 1052 | 0 | 62% | -226 | 652.24 | No | 0 | No
P071 | Shopping Mall Renovation Project 071 | Renovation | Pennsylvania | 2024-10-02 | 2024-02-17 | 2024-02-01 | Feb-24 | On Track | High | T003 | Task 003 of Shopping Mall Renovation Project 071 | Completed | Alice | 10 | 7325 | 6853 | 100% | -228 | 7325 | No | 0 | Yes
P072 | University Dormitory Construction Project 072 | Construction | Ohio | 2024-04-23 | 2025-05-27 | 2025-05-01 | May-25 | On Hold | High | T001 | Task 001 of University Dormitory Construction Project 072 | In Progress | Frank | 20 | 7862 | 0 | 77% | 399 | 6053.74 | No | 0 | No
P072 | University Dormitory Construction Project 072 | Construction | Georgia | 2024-04-23 | 2024-05-26 | 2024-05-01 | May-24 | On Hold | High | T002 | Task 002 of University Dormitory Construction Project 072 | Completed | Bob | 29 | 7708 | 7268 | 100% | 33 | 7708 | No | 0 | Yes
P072 | University Dormitory Construction Project 072 | Construction | New Jersey | 2024-04-23 | 2025-06-09 | 2025-06-01 | Jun-25 | On Hold | Medium | T003 | Task 003 of University Dormitory Construction Project 072 | Pending | Alice | 0 | 3260 | 0 | 36% | 412 | 1173.6 | No | 0 | No
P073 | Sports Stadium Upgrade Project 073 | Other | Texas | 2024-06-05 | 2024-09-23 | 2024-09-01 | Sep-24 | Behind | Low | T001 | Task 001 of Sports Stadium Upgrade Project 073 | Completed | Alice | 29 | 1702 | 1411 | 100% | 110 | 1702 | No | 0 | Yes
P073 | Sports Stadium Upgrade Project 073 | Other | Virginia | 2024-06-05 | 2024-08-22 | 2024-08-01 | Aug-24 | Behind | High | T002 | Task 002 of Sports Stadium Upgrade Project 073 | Completed | Bob | 24 | 8403 | 8115 | 100% | 78 | 8403 | No | 0 | Yes
P073 | Sports Stadium Upgrade Project 073 | Other | Texas | 2024-06-05 | 2024-09-14 | 2024-09-01 | Sep-24 | Behind | High | T003 | Task 003 of Sports Stadium Upgrade Project 073 | Completed | David | 14 | 4955 | 4586 | 100% | 101 | 4955 | No | 0 | Yes
P074 | Public Library Renovation Project 074 | Renovation | New York | 2024-05-21 | 2024-07-26 | 2024-07-01 | Jul-24 | Behind | High | T001 | Task 001 of Public Library Renovation Project 074 | Pending | Grace | 13 | 3533 | 0 | 74% | 66 | 2614.42 | No | 0 | No
P074 | Public Library Renovation Project 074 | Renovation | Washington | 2024-05-21 | 2024-08-01 | 2024-08-01 | Aug-24 | Behind | High | T002 | Task 002 of Public Library Renovation Project 074 | Pending | Alice | 8 | 8279 | 0 | 18% | 72 | 1490.22 | No | 0 | No
P074 | Public Library Renovation Project 074 | Renovation | Texas | 2024-05-21 | 2024-07-17 | 2024-07-01 | Jul-24 | Behind | High | T003 | Task 003 of Public Library Renovation Project 074 | In Progress | Charlie | 39 | 3680 | 0 | 5% | 57 | 184 | No | 0 | No
P075 | Building a Park Project 075 | Other | Texas | 2024-11-05 | 2024-06-13 | 2024-06-01 | Jun-24 | Behind | Medium | T001 | Task 001 of Building a Park Project 075 | Completed | Ivy | 11 | 8493 | 12398 | 100% | -145 | 8493 | Yes | 3905 | Yes
P075 | Building a Park Project 075 | Other | Washington | 2024-11-05 | 2025-09-12 | 2025-09-01 | Sep-25 | Behind | Medium | T002 | Task 002 of Building a Park Project 075 | Pending | Alice | 11 | 3828 | 0 | 26% | 311 | 995.28 | No | 0 | No
P075 | Building a Park Project 075 | Other | Virginia | 2024-11-05 | 2025-07-26 | 2025-07-01 | Jul-25 | Behind | Medium | T003 | Task 003 of Building a Park Project 075 | In Progress | Bob | 0 | 6118 | 0 | 29% | 263 | 1774.22 | No | 0 | No
P076 | Renovation of a School Project 076 | Renovation | Michigan | 2024-11-07 | 2024-08-01 | 2024-08-01 | Aug-24 | On Track | High | T001 | Task 001 of Renovation of a School Project 076 | Pending | Bob | 15 | 6558 | 0 | 71% | -98 | 4656.18 | No | 0 | No
P076 | Renovation of a School Project 076 | Renovation | New York | 2024-11-07 | 2024-08-11 | 2024-08-01 | Aug-24 | On Track | Medium | T002 | Task 002 of Renovation of a School Project 076 | Completed | Eve | 19 | 1044 | 899 | 100% | -88 | 1044 | No | 0 | Yes
P076 | Renovation of a School Project 076 | Renovation | Ohio | 2024-11-07 | 2024-08-01 | 2024-08-01 | Aug-24 | On Track | High | T003 | Task 003 of Renovation of a School Project 076 | Pending | Eve | 10 | 7397 | 0 | 21% | -98 | 1553.37 | No | 0 | No
P077 | Innovation of a Classroom Project 077 | Innovation | California | 2024-09-04 | 2025-02-07 | 2025-02-01 | Feb-25 | On Hold | Medium | T001 | Task 001 of Innovation of a Classroom Project 077 | In Progress | Eve | 2 | 8832 | 0 | 85% | 156 | 7507.2 | No | 0 | No
P077 | Innovation of a Classroom Project 077 | Innovation | Virginia | 2024-09-04 | 2024-05-12 | 2024-05-01 | May-24 | On Hold | High | T002 | Task 002 of Innovation of a Classroom Project 077 | Completed | Charlie | 39 | 3123 | 2841 | 100% | -115 | 3123 | No | 0 | Yes
P077 | Innovation of a Classroom Project 077 | Innovation | Florida | 2024-09-04 | 2025-03-13 | 2025-03-01 | Mar-25 | On Hold | Low | T003 | Task 003 of Innovation of a Classroom Project 077 | Pending | David | 1 | 6854 | 0 | 15% | 190 | 1028.1 | No | 0 | No
P078 | Construction of a Hospital Wing Project 078 | Construction | Michigan | 2024-01-26 | 2024-04-19 | 2024-04-01 | Apr-24 | On Hold | High | T001 | Task 001 of Construction of a Hospital Wing Project 078 | Completed | Alice | 25 | 8429 | 8416 | 100% | 84 | 8429 | No | 0 | Yes
P078 | Construction of a Hospital Wing Project 078 | Construction | New Jersey | 2024-01-26 | 2024-03-18 | 2024-03-01 | Mar-24 | On Hold | High | T002 | Task 002 of Construction of a Hospital Wing Project 078 | In Progress | Grace | 4 | 1501 | 0 | 95% | 52 | 1425.95 | No | 0 | No
P078 | Construction of a Hospital Wing Project 078 | Construction | Pennsylvania | 2024-01-26 | 2024-04-09 | 2024-04-01 | Apr-24 | On Hold | Medium | T003 | Task 003 of Construction of a Hospital Wing Project 078 | Completed | Alice | 12 | 8487 | 8486 | 100% | 74 | 8487 | No | 0 | Yes
P079 | Road Expansion Project 079 | Infrastructure | California | 2024-04-22 | 2025-01-13 | 2025-01-01 | Jan-25 | Completed | High | T001 | Task 001 of Road Expansion Project 079 | In Progress | Grace | 13 | 6425 | 0 | 11% | 266 | 706.75 | No | 0 | No
P079 | Road Expansion Project 079 | Infrastructure | Florida | 2024-04-22 | 2025-03-15 | 2025-03-01 | Mar-25 | Completed | High | T002 | Task 002 of Road Expansion Project 079 | In Progress | Ivy | 34 | 8044 | 0 | 5% | 327 | 402.2 | No | 0 | No
P079 | Road Expansion Project 079 | Infrastructure | New York | 2024-04-22 | 2024-05-25 | 2024-05-01 | May-24 | Completed | Medium | T003 | Task 003 of Road Expansion Project 079 | Completed | Charlie | 13 | 9524 | 9474 | 100% | 33 | 9524 | No | 0 | Yes
P080 | Bridge Maintenance Project 080 | Maintenance | Ohio | 2024-04-16 | 2024-07-09 | 2024-07-01 | Jul-24 | On Track | High | T001 | Task 001 of Bridge Maintenance Project 080 | Pending | Eve | 13 | 4368 | 0 | 70% | 84 | 3057.6 | No | 0 | No
P080 | Bridge Maintenance Project 080 | Maintenance | New Jersey | 2024-04-16 | 2024-06-23 | 2024-06-01 | Jun-24 | On Track | Low | T002 | Task 002 of Bridge Maintenance Project 080 | In Progress | Grace | 15 | 2261 | 0 | 65% | 68 | 1469.65 | No | 0 | No
P080 | Bridge Maintenance Project 080 | Maintenance | Texas | 2024-04-16 | 2024-07-06 | 2024-07-01 | Jul-24 | On Track | Medium | T003 | Task 003 of Bridge Maintenance Project 080 | Completed | Alice | 27 | 8706 | 8333 | 100% | 81 | 8706 | No | 0 | Yes
P081 | Office Building Renovation Project 081 | Renovation | Pennsylvania | 2024-05-31 | 2025-01-04 | 2025-01-01 | Jan-25 | On Track | High | T001 | Task 001 of Office Building Renovation Project 081 | In Progress | Alice | 26 | 1149 | 0 | 8% | 218 | 91.92 | No | 0 | No
P081 | Office Building Renovation Project 081 | Renovation | Virginia | 2024-05-31 | 2025-03-03 | 2025-03-01 | Mar-25 | On Track | Medium | T002 | Task 002 of Office Building Renovation Project 081 | In Progress | Frank | 5 | 5011 | 0 | 9% | 276 | 450.99 | No | 0 | No
P081 | Office Building Renovation Project 081 | Renovation | North Carolina | 2024-05-31 | 2024-07-03 | 2024-07-01 | Jul-24 | On Track | High | T003 | Task 003 of Office Building Renovation Project 081 | Completed | Ivy | 5 | 6163 | 5756 | 100% | 33 | 6163 | No | 0 | Yes
P082 | Apartment Complex Development Project 082 | Other | Ohio | 2024-01-07 | 2025-03-12 | 2025-03-01 | Mar-25 | On Track | Medium | T001 | Task 001 of Apartment Complex Development Project 082 | In Progress | Ivy | 4 | 7524 | 0 | 47% | 430 | 3536.28 | No | 0 | No
P082 | Apartment Complex Development Project 082 | Other | Florida | 2024-01-07 | 2024-09-25 | 2024-09-01 | Sep-24 | On Track | Medium | T002 | Task 002 of Apartment Complex Development Project 082 | Completed | Grace | 10 | 2202 | 1878 | 100% | 262 | 2202 | No | 0 | Yes
P082 | Apartment Complex Development Project 082 | Other | Pennsylvania | 2024-01-07 | 2025-03-17 | 2025-03-01 | Mar-25 | On Track | High | T003 | Task 003 of Apartment Complex Development Project 082 | In Progress | Ivy | 21 | 6835 | 0 | 58% | 435 | 3964.3 | No | 0 | No
P083 | Commercial Center Construction Project 083 | Construction | Michigan | 2024-03-20 | 2024-06-05 | 2024-06-01 | Jun-24 | Behind | Medium | T001 | Task 001 of Commercial Center Construction Project 083 | Completed | Alice | 24 | 8645 | 8633 | 100% | 77 | 8645 | No | 0 | Yes
P083 | Commercial Center Construction Project 083 | Construction | New York | 2024-03-20 | 2024-05-25 | 2024-05-01 | May-24 | Behind | High | T002 | Task 002 of Commercial Center Construction Project 083 | Completed | Charlie | 19 | 9360 | 9196 | 100% | 66 | 9360 | No | 0 | Yes
P083 | Commercial Center Construction Project 083 | Construction | Georgia | 2024-03-20 | 2024-06-15 | 2024-06-01 | Jun-24 | Behind | High | T003 | Task 003 of Commercial Center Construction Project 083 | In Progress | Charlie | 28 | 2183 | 0 | 37% | 87 | 807.71 | No | 0 | No
P084 | Highway Reconstruction Project 084 | Other | Georgia | 2024-09-06 | 2025-05-08 | 2025-05-01 | May-25 | On Hold | Low | T001 | Task 001 of Highway Reconstruction Project 084 | Pending | Charlie | 17 | 1713 | 0 | 54% | 244 | 925.02 | No | 0 | No
P084 | Highway Reconstruction Project 084 | Other | North Carolina | 2024-09-06 | 2025-04-19 | 2025-04-01 | Apr-25 | On Hold | Medium | T002 | Task 002 of Highway Reconstruction Project 084 | In Progress | Ivy | 16 | 6400 | 0 | 91% | 225 | 5824 | No | 0 | No
P084 | Highway Reconstruction Project 084 | Other | North Carolina | 2024-09-06 | 2025-03-25 | 2025-03-01 | Mar-25 | On Hold | High | T003 | Task 003 of Highway Reconstruction Project 084 | Pending | Eve | 14 | 3319 | 0 | 20% | 200 | 663.8 | No | 0 | No
P085 | Airport Expansion Project 085 | Other | Virginia | 2024-03-08 | 2024-11-18 | 2024-11-01 | Nov-24 | Completed | Low | T001 | Task 001 of Airport Expansion Project 085 | Pending | Alice | 17 | 8340 | 0 | 2% | 255 | 166.8 | No | 0 | No
P085 | Airport Expansion Project 085 | Other | Illinois | 2024-03-08 | 2024-09-25 | 2024-09-01 | Sep-24 | Completed | High | T002 | Task 002 of Airport Expansion Project 085 | Completed | David | 15 | 4749 | 4572 | 100% | 201 | 4749 | No | 0 | Yes
P085 | Airport Expansion Project 085 | Other | New Jersey | 2024-03-08 | 2024-11-19 | 2024-11-01 | Nov-24 | Completed | High | T003 | Task 003 of Airport Expansion Project 085 | Pending | Alice | 24 | 6222 | 0 | 51% | 256 | 3173.22 | No | 0 | No
P086 | Shopping Mall Renovation Project 086 | Renovation | Pennsylvania | 2024-01-29 | 2024-12-10 | 2024-12-01 | Dec-24 | Completed | High | T001 | Task 001 of Shopping Mall Renovation Project 086 | In Progress | Eve | 35 | 9246 | 0 | 54% | 316 | 4992.84 | No | 0 | No
P086 | Shopping Mall Renovation Project 086 | Renovation | Pennsylvania | 2024-01-29 | 2024-09-25 | 2024-09-01 | Sep-24 | Completed | High | T002 | Task 002 of Shopping Mall Renovation Project 086 | Completed | Eve | 6 | 7327 | 7120 | 100% | 240 | 7327 | No | 0 | Yes
P086 | Shopping Mall Renovation Project 086 | Renovation | Virginia | 2024-01-29 | 2024-10-17 | 2024-10-01 | Oct-24 | Completed | High | T003 | Task 003 of Shopping Mall Renovation Project 086 | Pending | Alice | 19 | 6331 | 0 | 25% | 262 | 1582.75 | No | 0 | No
P087 | University Dormitory Construction Project 087 | Construction | California | 2024-02-17 | 2025-09-11 | 2025-09-01 | Sep-25 | On Track | High | T001 | Task 001 of University Dormitory Construction Project 087 | In Progress | Frank | 8 | 2256 | 0 | 6% | 572 | 135.36 | No | 0 | No
P087 | University Dormitory Construction Project 087 | Construction | New York | 2024-02-17 | 2025-10-07 | 2025-10-01 | Oct-25 | On Track | Medium | T002 | Task 002 of University Dormitory Construction Project 087 | Pending | Bob | 1 | 5371 | 0 | 45% | 598 | 2416.95 | No | 0 | No
P087 | University Dormitory Construction Project 087 | Construction | North Carolina | 2024-02-17 | 2025-10-06 | 2025-10-01 | Oct-25 | On Track | High | T003 | Task 003 of University Dormitory Construction Project 087 | In Progress | Alice | 12 | 2434 | 0 | 30% | 597 | 730.2 | No | 0 | No
P088 | Sports Stadium Upgrade Project 088 | Other | Georgia | 2024-07-21 | 2025-02-13 | 2025-02-01 | Feb-25 | Completed | High | T001 | Task 001 of Sports Stadium Upgrade Project 088 | In Progress | Alice | 16 | 7504 | 0 | 29% | 207 | 2176.16 | No | 0 | No
P088 | Sports Stadium Upgrade Project 088 | Other | Virginia | 2024-07-21 | 2025-02-02 | 2025-02-01 | Feb-25 | Completed | Medium | T002 | Task 002 of Sports Stadium Upgrade Project 088 | Pending | Bob | 30 | 7717 | 0 | 48% | 196 | 3704.16 | No | 0 | No
P088 | Sports Stadium Upgrade Project 088 | Other | Washington | 2024-07-21 | 2024-12-21 | 2024-12-01 | Dec-24 | Completed | High | T003 | Task 003 of Sports Stadium Upgrade Project 088 | In Progress | David | 18 | 4651 | 0 | 77% | 153 | 3581.27 | No | 0 | No
P089 | Public Library Renovation Project 089 | Renovation | Georgia | 2024-05-26 | 2025-05-06 | 2025-05-01 | May-25 | On Track | Medium | T001 | Task 001 of Public Library Renovation Project 089 | In Progress | Grace | 17 | 5791 | 0 | 75% | 345 | 4343.25 | No | 0 | No
P089 | Public Library Renovation Project 089 | Renovation | Washington | 2024-05-26 | 2025-07-18 | 2025-07-01 | Jul-25 | On Track | High | T002 | Task 002 of Public Library Renovation Project 089 | In Progress | Alice | 4 | 4133 | 0 | 23% | 418 | 950.59 | No | 0 | No
P089 | Public Library Renovation Project 089 | Renovation | Washington | 2024-05-26 | 2024-06-28 | 2024-06-01 | Jun-24 | On Track | Medium | T003 | Task 003 of Public Library Renovation Project 089 | Completed | Charlie | 34 | 8716 | 8476 | 100% | 33 | 8716 | No | 0 | Yes
P090 | Building a Park Project 090 | Other | Michigan | 2024-11-06 | 2024-07-14 | 2024-07-01 | Jul-24 | Completed | High | T001 | Task 001 of Building a Park Project 090 | Completed | Ivy | 21 | 9174 | 9031 | 100% | -115 | 9174 | No | 0 | Yes
P090 | Building a Park Project 090 | Other | North Carolina | 2024-11-06 | 2025-09-01 | 2025-09-01 | Sep-25 | Completed | Low | T002 | Task 002 of Building a Park Project 090 | In Progress | Alice | 27 | 9702 | 0 | 8% | 299 | 776.16 | No | 0 | No
P090 | Building a Park Project 090 | Other | Georgia | 2024-11-06 | 2025-10-21 | 2025-10-01 | Oct-25 | Completed | High | T003 | Task 003 of Building a Park Project 090 | In Progress | Bob | 21 | 8975 | 0 | 96% | 349 | 8616 | No | 0 | No
P091 | Renovation of a School Project 091 | Renovation | Michigan | 2024-05-22 | 2024-06-24 | 2024-06-01 | Jun-24 | On Hold | High | T001 | Task 001 of Renovation of a School Project 091 | Completed | Bob | 23 | 7491 | 7138 | 100% | 33 | 7491 | No | 0 | Yes
P091 | Renovation of a School Project 091 | Renovation | Michigan | 2024-05-22 | 2025-03-13 | 2025-03-01 | Mar-25 | On Hold | Medium | T002 | Task 002 of Renovation of a School Project 091 | Pending | Eve | 22 | 4013 | 0 | 92% | 295 | 3691.96 | No | 0 | No
P091 | Renovation of a School Project 091 | Renovation | New York | 2024-05-22 | 2025-03-21 | 2025-03-01 | Mar-25 | On Hold | Low | T003 | Task 003 of Renovation of a School Project 091 | Pending | Eve | 33 | 1670 | 0 | 64% | 303 | 1068.8 | No | 0 | No
P092 | Innovation of a Classroom Project 092 | Innovation | California | 2024-03-03 | 2024-11-26 | 2024-11-01 | Nov-24 | Completed | Medium | T001 | Task 001 of Innovation of a Classroom Project 092 | Pending | Eve | 22 | 6004 | 0 | 4% | 268 | 240.16 | No | 0 | No
P092 | Innovation of a Classroom Project 092 | Innovation | Illinois | 2024-03-03 | 2024-09-25 | 2024-09-01 | Sep-24 | Completed | Medium | T002 | Task 002 of Innovation of a Classroom Project 092 | Completed | Charlie | 13 | 9649 | 9485 | 100% | 206 | 9649 | No | 0 | Yes
P092 | Innovation of a Classroom Project 092 | Innovation | Georgia | 2024-03-03 | 2024-09-25 | 2024-09-01 | Sep-24 | Completed | High | T003 | Task 003 of Innovation of a Classroom Project 092 | Completed | David | 11 | 5921 | 5788 | 100% | 206 | 5921 | No | 0 | Yes
P093 | Construction of a Hospital Wing Project 093 | Construction | Virginia | 2024-08-19 | 2024-09-21 | 2024-09-01 | Sep-24 | Completed | Low | T001 | Task 001 of Construction of a Hospital Wing Project 093 | Completed | Alice | 40 | 4306 | 3888 | 100% | 33 | 4306 | No | 0 | Yes
P093 | Construction of a Hospital Wing Project 093 | Construction | Illinois | 2024-08-19 | 2025-04-19 | 2025-04-01 | Apr-25 | Completed | Low | T002 | Task 002 of Construction of a Hospital Wing Project 093 | In Progress | Grace | 31 | 8367 | 0 | 75% | 243 | 6275.25 | No | 0 | No
P093 | Construction of a Hospital Wing Project 093 | Construction | Georgia | 2024-08-19 | 2024-09-21 | 2024-09-01 | Sep-24 | Completed | Low | T003 | Task 003 of Construction of a Hospital Wing Project 093 | Completed | Charlie | 0 | 4178 | 4148 | 100% | 33 | 4178 | No | 0 | Yes
P094 | Road Expansion Project 094 | Infrastructure | North Carolina | 2024-06-28 | 2024-10-06 | 2024-10-01 | Oct-24 | Behind | High | T001 | Task 001 of Road Expansion Project 094 | In Progress | Grace | 13 | 1773 | 0 | 44% | 100 | 780.12 | No | 0 | No
P094 | Road Expansion Project 094 | Infrastructure | Illinois | 2024-06-28 | 2024-09-29 | 2024-09-01 | Sep-24 | Behind | High | T002 | Task 002 of Road Expansion Project 094 | In Progress | Ivy | 20 | 7829 | 0 | 42% | 93 | 3288.18 | No | 0 | No
P094 | Road Expansion Project 094 | Infrastructure | Virginia | 2024-06-28 | 2024-09-23 | 2024-09-01 | Sep-24 | Behind | Medium | T003 | Task 003 of Road Expansion Project 094 | In Progress | Charlie | 39 | 1447 | 3357 | 37% | 87 | 535.39 | Yes | 1910 | Yes
P095 | Bridge Maintenance Project 095 | Maintenance | Ohio | 2024-02-17 | 2024-08-02 | 2024-08-01 | Aug-24 | Behind | Medium | T001 | Task 001 of Bridge Maintenance Project 095 | Pending | Eve | 24 | 8329 | 0 | 81% | 167 | 6746.49 | No | 0 | No
P095 | Bridge Maintenance Project 095 | Maintenance | Illinois | 2024-02-17 | 2024-06-29 | 2024-06-01 | Jun-24 | Behind | Low | T002 | Task 002 of Bridge Maintenance Project 095 | In Progress | Grace | 34 | 6160 | 0 | 97% | 133 | 5975.2 | No | 0 | No
P095 | Bridge Maintenance Project 095 | Maintenance | New Jersey | 2024-02-17 | 2024-07-27 | 2024-07-01 | Jul-24 | Behind | High | T003 | Task 003 of Bridge Maintenance Project 095 | In Progress | Charlie | 7 | 6083 | 0 | 58% | 161 | 3528.14 | No | 0 | No
P096 | Office Building Renovation Project 096 | Renovation | Georgia | 2024-03-03 | 2025-05-06 | 2025-05-01 | May-25 | On Track | Low | T001 | Task 001 of Office Building Renovation Project 096 | Pending | Alice | 17 | 1235 | 0 | 69% | 429 | 852.15 | No | 0 | No
P096 | Office Building Renovation Project 096 | Renovation | Illinois | 2024-03-03 | 2025-01-05 | 2025-01-01 | Jan-25 | On Track | Medium | T002 | Task 002 of Office Building Renovation Project 096 | In Progress | Frank | 20 | 2984 | 6060 | 8% | 308 | 238.72 | Yes | 3076 | Yes
P096 | Office Building Renovation Project 096 | Renovation | Ohio | 2024-03-03 | 2025-03-09 | 2025-03-01 | Mar-25 | On Track | High | T003 | Task 003 of Office Building Renovation Project 096 | Pending | Ivy | 32 | 5211 | 0 | 92% | 371 | 4794.12 | No | 0 | No
P097 | Apartment Complex Development Project 097 | Other | Washington | 2024-08-06 | 2024-12-08 | 2024-12-01 | Dec-24 | Behind | High | T001 | Task 001 of Apartment Complex Development Project 097 | Pending | Ivy | 9 | 6292 | 0 | 50% | 124 | 3146 | No | 0 | No
P097 | Apartment Complex Development Project 097 | Other | Florida | 2024-08-06 | 2025-03-08 | 2025-03-01 | Mar-25 | Behind | Medium | T002 | Task 002 of Apartment Complex Development Project 097 | Pending | Grace | 17 | 2335 | 0 | 20% | 214 | 467 | No | 0 | No
P097 | Apartment Complex Development Project 097 | Other | Virginia | 2024-08-06 | 2024-12-21 | 2024-12-01 | Dec-24 | Behind | High | T003 | Task 003 of Apartment Complex Development Project 097 | Pending | Ivy | 32 | 3956 | 0 | 66% | 137 | 2610.96 | No | 0 | No
P098 | Commercial Center Construction Project 098 | Construction | Illinois | 2024-08-15 | 2025-01-23 | 2025-01-01 | Jan-25 | Completed | Medium | T001 | Task 001 of Commercial Center Construction Project 098 | In Progress | Alice | 12 | 8906 | 0 | 67% | 161 | 5967.02 | No | 0 | No
P098 | Commercial Center Construction Project 098 | Construction | Texas | 2024-08-15 | 2025-01-28 | 2025-01-01 | Jan-25 | Completed | Medium | T002 | Task 002 of Commercial Center Construction Project 098 | Pending | Charlie | 25 | 8346 | 0 | 83% | 166 | 6927.18 | No | 0 | No
P098 | Commercial Center Construction Project 098 | Construction | Michigan | 2024-08-15 | 2025-04-27 | 2025-04-01 | Apr-25 | Completed | High | T003 | Task 003 of Commercial Center Construction Project 098 | In Progress | Charlie | 20 | 5134 | 0 | 30% | 255 | 1540.2 | No | 0 | No
P099 | Highway Reconstruction Project 099 | Other | New Jersey | 2024-05-31 | 2024-12-22 | 2024-12-01 | Dec-24 | Completed | Medium | T001 | Task 001 of Highway Reconstruction Project 099 | Pending | Charlie | 7 | 7307 | 0 | 14% | 205 | 1022.98 | No | 0 | No
P099 | Highway Reconstruction Project 099 | Other | New York | 2024-05-31 | 2025-03-01 | 2025-03-01 | Mar-25 | Completed | High | T002 | Task 002 of Highway Reconstruction Project 099 | Pending | Ivy | 5 | 9425 | 0 | 36% | 274 | 3393 | No | 0 | No
P099 | Highway Reconstruction Project 099 | Other | Florida | 2024-05-31 | 2025-03-11 | 2025-03-01 | Mar-25 | Completed | High | T003 | Task 003 of Highway Reconstruction Project 099 | Pending | Eve | 19 | 5199 | 0 | 91% | 284 | 4731.09 | No | 0 | No
P100 | Airport Expansion Project 100 | Other | Virginia | 2024-08-08 | 2024-09-02 | 2024-09-01 | Sep-24 | On Track | Medium | T001 | Task 001 of Airport Expansion Project 100 | Pending | Charlie | 30 | 2156 | 0 | 85% | 25 | 1832.6 | No | 0 | No
P100 | Airport Expansion Project 100 | Other | Pennsylvania | 2024-08-08 | 2024-08-30 | 2024-08-01 | Aug-24 | On Track | Medium | T002 | Task 002 of Airport Expansion Project 100 | Pending | David | 12 | 1502 | 0 | 2% | 22 | 30.04 | No | 0 | No
P100 | Airport Expansion Project 100 | Other | Virginia | 2024-08-08 | 2024-08-30 | 2024-08-01 | Aug-24 | On Track | Medium | T003 | Task 003 of Airport Expansion Project 100 | In Progress | Alice | 38 | 8619 | 0 | 86% | 22 | 7412.34 | No | 0 | No